## Transmittal
PROJECT NAME : GG |  |  | TRANSMITTAL NO: TR-004
FABRICATOR : GG |  |  | DATE: 03/05/2026
Sl. No. | Sheet No. | Drawing Title | Sent for Fabrication |  | Revision History
|  |  | REV# | DATE
DETAIL SHEETS
1 | F-03.00 | PLATE DETAIL | 0 | 09-22-2025 | For Fabrication
2 | F-03.00 | PLATE DETAIL | 0 | 09-22-2025 | For Fabrication
3 | F-03.00 | PLATE DETAIL | 0 | 09-22-2025 | For Fabrication
4 | F-03.01 | COLUMN DETAIL | 2 | 09-25-2025 | Revised as noted
5 | F-03.01 | COLUMN DETAIL | 2 | 09-25-2025 | Revised as noted
6 | F-03.01 | COLUMN DETAIL | 2 | 09-25-2025 | Revised as noted
7 | F-03.02 | COLUMN DETAIL | 1 | 09-25-2025 | Revised as noted
8 | F-03.02 | COLUMN DETAIL | 1 | 09-25-2025 | Revised as noted
9 | F-03.02 | COLUMN DETAIL | 1 | 09-25-2025 | Revised as noted
10 | F-03.03 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication
11 | F-03.03 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication
12 | F-03.03 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication
13 | F-03.04 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication
14 | F-03.04 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication
15 | F-03.04 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication
16 | F-03.05 | COLUMN & BEAM DETAIL | 1 | 09-25-2025 | Revised as noted
17 | F-03.05 | COLUMN & BEAM DETAIL | 1 | 09-25-2025 | Revised as noted
18 | F-03.05 | COLUMN & BEAM DETAIL | 1 | 09-25-2025 | Revised as noted
19 | F-03.06 | BEAM DETAIL | 1 | 09-25-2025 | Revised as noted
20 | F-03.06 | BEAM DETAIL | 1 | 09-25-2025 | Revised as noted
21 | F-03.06 | BEAM DETAIL | 1 | 09-25-2025 | Revised as noted
22 | F-03.07 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
23 | F-03.07 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
24 | F-03.07 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
25 | F-03.08 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
26 | F-03.08 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
27 | F-03.08 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
28 | F-03.09 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
29 | F-03.09 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
30 | F-03.09 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication
31 | F-03.11 | MISCELLANEOUS DETAIL | 1 | 09-25-2025 | Revised as noted
32 | F-03.11 | MISCELLANEOUS DETAIL | 1 | 09-25-2025 | Revised as noted
33 | F-03.11 | MISCELLANEOUS DETAIL | 1 | 09-25-2025 | Revised as noted
34 | F-03.12 | MISCELLANEOUS DETAIL | 2 | 09-25-2025 | Revised as noted
35 | F-03.12 | MISCELLANEOUS DETAIL | 2 | 09-25-2025 | Revised as noted
36 | F-03.12 | MISCELLANEOUS DETAIL | 2 | 09-25-2025 | Revised as noted
DRAWINGS
37 | E-03.01D | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
E-SHEETS
38 | E-03.00 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
39 | E-03.00 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
40 | E-03.00 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
41 | E-03.00A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
42 | E-03.00A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
43 | E-03.00A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
44 | E-03.01 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
45 | E-03.01 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
46 | E-03.01 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
47 | E-03.01A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
48 | E-03.01A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
49 | E-03.01A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
50 | E-03.01B | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
51 | E-03.01B | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
52 | E-03.01B | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
53 | E-03.01C | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
54 | E-03.01C | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
55 | E-03.01C | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
56 | E-03.01D | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
57 | E-03.01D | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
58 | E-03.01D | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
59 | E-03.01E | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
60 | E-03.01E | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
61 | E-03.01E | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
62 | E-03.01F | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
63 | E-03.01F | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
64 | E-03.01F | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction
65 | E-03.02 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
66 | E-03.02 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
67 | E-03.02 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
68 | E-03.03 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
69 | E-03.03 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
70 | E-03.03 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
71 | E-03.04 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
72 | E-03.04 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
73 | E-03.04 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction
74 | E-03.05 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
75 | E-03.05 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
76 | E-03.05 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
77 | E-03.06 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
78 | E-03.06 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
79 | E-03.06 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
80 | E-03.07 | SOW #03 -SOUTH WEST FRAMING SECTIONS Scale VARIES TUORG KNIRHS-NON | 0 | 09-25-2025 | For Construction
81 | E-03.07 | SOW #03 -SOUTH WEST FRAMING SECTIONS Scale VARIES TUORG KNIRHS-NON | 0 | 09-25-2025 | For Construction
82 | E-03.07 | SOW #03 -SOUTH WEST FRAMING SECTIONS Scale VARIES TUORG KNIRHS-NON | 0 | 09-25-2025 | For Construction
83 | E-03.08 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
84 | E-03.08 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
85 | E-03.08 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
86 | E-03.09 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
87 | E-03.09 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
88 | E-03.09 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction
GATHER SHEET
89 | a738 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
90 | a738 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
91 | a738 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
92 | a1095 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
93 | a1095 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
94 | a1095 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
95 | a1136 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
96 | a1136 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
97 | a1136 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
98 | a2573 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
99 | a2573 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
100 | a2573 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
101 | a3514 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
102 | a3514 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
103 | a3514 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION
104 | bp1000 | BASE PLATE | 0
105 | bp1000 | BASE PLATE | 0
106 | bp1000 | BASE PLATE | 0
107 | bp1001 | BASE PLATE | 0 | 09-22-2025 | FOR FABRICATION
108 | bp1001 | BASE PLATE | 0 | 09-22-2025 | FOR FABRICATION
109 | bp1001 | BASE PLATE | 0 | 09-22-2025 | FOR FABRICATION
110 | bpl1994 | BENT PLATE | 0 | 09-22-2025 | FOR FABRICATION
111 | bpl1994 | BENT PLATE | 0 | 09-22-2025 | FOR FABRICATION
112 | bpl1994 | BENT PLATE | 0 | 09-22-2025 | FOR FABRICATION
113 | cp1000 | CAP PLATE | 0 | 09-22-2025 | FOR FABRICATION
114 | cp1000 | CAP PLATE | 0 | 09-22-2025 | FOR FABRICATION
115 | cp1000 | CAP PLATE | 0 | 09-22-2025 | FOR FABRICATION
116 | cp1001 | CAP PLATE | 2 | 09-25-2025 | REVISED AS NOTED
117 | cp1001 | CAP PLATE | 2 | 09-25-2025 | REVISED AS NOTED
118 | cp1001 | CAP PLATE | 2 | 09-25-2025 | REVISED AS NOTED
119 | pl462 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
120 | pl462 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
121 | pl462 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
122 | pl470 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
123 | pl470 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
124 | pl470 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
125 | pl472 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
126 | pl472 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
127 | pl472 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
128 | pl473 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
129 | pl473 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
130 | pl473 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
131 | pl658 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
132 | pl658 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
133 | pl658 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
134 | pl665 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
135 | pl665 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
136 | pl665 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
137 | pl680 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
138 | pl680 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
139 | pl680 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
140 | pl1517 | PLATE | 0
141 | pl1517 | PLATE | 0
142 | pl1517 | PLATE | 0
143 | pl1550 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
144 | pl1550 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
145 | pl1550 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
146 | pl1608 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
147 | pl1608 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
148 | pl1608 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
149 | pl2938 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
150 | pl2938 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
151 | pl2938 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
152 | pl3056 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
153 | pl3056 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
154 | pl3056 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
155 | pl3057 | PLATE | 0
156 | pl3057 | PLATE | 0
157 | pl3057 | PLATE | 0
158 | pl3732 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
159 | pl3732 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
160 | pl3732 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
161 | pl3738 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
162 | pl3738 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
163 | pl3738 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED
164 | pl3739 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
165 | pl3739 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
166 | pl3739 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
167 | pl3740 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
168 | pl3740 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
169 | pl3740 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
170 | pl3742 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
171 | pl3742 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
172 | pl3742 | PLATE | 0 | 09-22-2025 | FOR FABRICATION
173 | pl3749 | PLATE | 0 | 09-25-2025 | FOR FABRICATION
174 | pl3749 | PLATE | 0 | 09-25-2025 | FOR FABRICATION
175 | pl3749 | PLATE | 0 | 09-25-2025 | FOR FABRICATION