## Drawing Log
OUTGOING DRAWING LOG SHEET
Project Name: hb |  |  |  | Client: n
Sl. No. | Sheet No. | Drawing Title | Sent for Approval | Sent for Fabrication |  |  | Remarks
|  |  | Rev A | Rev 0 | Rev 1 | Rev 2
DETAIL SHEETS
1 | 02B1000 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
2 | 02B1001 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
3 | 02B1002 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
4 | 02B1003 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
5 | 02B1004 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
6 | 02B1005 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
7 | 02B1006 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
8 | 02B1007 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
9 | 02B1008 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
10 | 02B1009 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
11 | 02B1010 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
12 | 02B1011 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
13 | 02B1012 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
14 | 02B1013 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
15 | 02B1014 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
16 | 02B1015 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
17 | 02B1016 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
18 | 02B1017 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
19 | 02B1018 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
20 | 02B1019 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
21 | 02B1020 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
22 | 02B1021 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
23 | 02B1022 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
24 | 02B1023 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
25 | 02B1024 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
26 | 02B1025 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
27 | 02B1026 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
28 | 02B1027 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
29 | 02B1028 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
30 | 02B1029 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
31 | 02B1030 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
32 | 02B1031 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
33 | 02B1032 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
34 | 02B1033 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
35 | 02B1034 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
36 | 02B1035 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
37 | 02B1036 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
38 | 02B1037 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
39 | 02B1038 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
40 | 02B1039 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
41 | 02B1040 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
42 | 02B1041 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
43 | 02B1042 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
44 | 02B1043 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
45 | 02B1044 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
46 | 02B1045 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
47 | 02B1046 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
48 | 02C1000 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
49 | 02C1001 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
50 | 02C1002 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
51 | 02C1003 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
52 | 02C1004 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
53 | 02C1005 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
54 | 02C1006 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
55 | 02C1007 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
56 | 02C1008 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
57 | 02C1009 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
58 | 02C1010 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
59 | 02C1011 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
60 | 02C1012 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
61 | 02C1013 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
62 | 02C1014 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
63 | 02C1015 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
64 | 02D1000 | HORIZONTAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
65 | 02D1001 | HORIZONTAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
66 | 02D1002 | HORIZONTAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
67 | 02D1003 | HORIZONTAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
68 | 02D1004 | VERTICAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
69 | 02D1005 | VERTICAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
70 | 02D1006 | VERTICAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
71 | 02D1007 | VERTICAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
72 | 02D1008 | VERTICAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
73 | 02D1009 | VERTICAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
74 | 02D1010 | VERTICAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
75 | 02D1011 | VERTICAL BRACE | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
76 | 02M1000 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
77 | 02M1001 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
78 | 02M1002 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
79 | 02M1003 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
80 | 02M1004 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
81 | 02M1005 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
82 | 02M1006 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
83 | 02M1007 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
84 | 02M1008 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
85 | 02M1009 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
86 | 02M1010 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
87 | 02M1011 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
88 | 02M1012 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
89 | 02M1013 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
90 | 02M1014 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
91 | 02M1015 | 02M1015 ONE ANGLE FRAME 178 178 | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
92 | 02M1016 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
93 | 02M1017 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
94 | 02M1018 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
95 | 02M1019 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
96 | 02M1020 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
97 | 02M1021 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
98 | 02M1022 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
99 | 02M1023 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
100 | 02M1024 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
101 | 02M1025 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
102 | 02M1026 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
103 | 02M1027 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
104 | 02M1028 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
105 | 02M1029 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
106 | 02M1030 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
107 | 02M1031 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
108 | 02M1032 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
109 | 02M1033 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
110 | 02M1034 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
111 | 02M1035 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
112 | 03B1000 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
113 | 03B1001 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
114 | 03B1002 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
115 | 03B1003 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
116 | 03B1004 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
117 | 03B1005 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
118 | 03B1006 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
119 | 03B1007 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
120 | 03B1008 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
121 | 03B1009 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
122 | 03B1010 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
123 | 03B1011 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
124 | 03B1012 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
125 | 03B1013 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
126 | 03B1014 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
127 | 03B1015 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
128 | 03B1016 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
129 | 03B1017 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
130 | 03B1018 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
131 | 03B1019 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
132 | 03B1020 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
133 | 03B1021 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
134 | 03B1022 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
135 | 03B1023 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
136 | 03B1024 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
137 | 03B1025 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
138 | 03B1026 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
139 | 03B1027 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
140 | 03B1028 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
141 | 03B1029 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
142 | 03B1030 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
143 | 03B1031 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
144 | 03B1032 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
145 | 03B1033 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
146 | 03B1034 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
147 | 03B1035 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
148 | 03B1036 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
149 | 03B1037 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
150 | 03B1038 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
151 | 03B1039 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
152 | 03B1040 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
153 | 03B1041 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
154 | 03B1042 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
155 | 03B1043 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
156 | 03B1044 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
157 | 03B1045 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
158 | 03B1046 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
159 | 03B1047 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
160 | 03B1048 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
161 | 03B1049 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
162 | 03B1050 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
163 | 03B1051 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
164 | 03B1052 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
165 | 03C1000 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
166 | 03C1001 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
167 | 03C1002 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
168 | 03C1003 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
169 | 03C1004 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
170 | 03C1005 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
171 | 03C1006 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
172 | 03C1007 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
173 | 03C1008 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
174 | 03C1009 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
175 | 03C1010 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
176 | 03C1011 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
177 | 03C1012 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
178 | 03C1013 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
179 | 03C1014 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
180 | 03C1015 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
181 | 03C1016 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
182 | 03C1017 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
183 | 03D1000 | HORIZONTAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
184 | 03D1001 | HORIZONTAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
185 | 03D1002 | HORIZONTAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
186 | 03D1003 | HORIZONTAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
187 | 03M1000 | BACKING BAR DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
188 | 03M1001 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
189 | 03M1002 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
190 | 03M1003 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
191 | 03M1004 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
192 | 03M1005 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
193 | 03M1006 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
194 | 03M1007 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
195 | 03M1008 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
196 | 03M1009 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
197 | 03M1010 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
198 | 03M1011 | HSS DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
199 | 03M1012 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
200 | 03M1013 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
201 | 03M1014 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
202 | 03M1015 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
203 | 03M1016 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
204 | 03M1017 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
205 | 03M1018 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
206 | 03M1019 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
207 | 03M1020 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
208 | 03M1021 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
209 | 03M1022 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
210 | 03M1023 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
211 | 03M1024 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
212 | 03M1025 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
213 | 03M1026 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
214 | 03M1027 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
215 | 03M1028 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
216 | 03M1029 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
217 | 03M1030 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
218 | 04B1000 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
219 | 04B1001 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
220 | 04B1002 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
221 | 04B1003 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
222 | 04B1004 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
223 | 04B1005 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
224 | 04B1006 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
225 | 04B1007 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
226 | 04B1008 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
227 | 04B1009 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
228 | 04B1010 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
229 | 04B1011 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
230 | 04B1012 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
231 | 04B1013 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
232 | 04B1014 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
233 | 04B1015 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
234 | 04B1016 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
235 | 04B1017 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
236 | 04B1018 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
237 | 04B1019 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
238 | 04B1020 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
239 | 04B1021 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
240 | 04B1022 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
241 | 04B1023 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
242 | 04B1024 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
243 | 04B1025 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
244 | 04C1000 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
245 | 04C1001 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
246 | 04C1002 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
247 | 04C1003 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
248 | 04C1004 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
249 | 04C1005 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
250 | 04C1006 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
251 | 04C1007 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
252 | 04C1008 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
253 | 04C1009 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
254 | 04D1000 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
255 | 04D1001 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
256 | 04D1002 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
257 | 04D1003 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
258 | 04D1004 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
259 | 04D1005 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
260 | 04M1000 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
261 | 04M1001 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
262 | 04M1002 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
263 | 04M1003 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
264 | 04M1004 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
265 | 04M1005 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
266 | 04M1006 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
267 | 04M1007 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
268 | 04M1008 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
269 | 04M1009 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
270 | 04M1010 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
271 | 04M1011 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
272 | 04M1012 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
273 | 04M1013 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
274 | 04M1014 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
275 | 04M1015 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
276 | 04M1016 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
277 | 04M1017 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
278 | 04M1018 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
279 | 04M1019 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
280 | 04M1020 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
281 | 04M1021 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
282 | 04M1022 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
283 | 04M1023 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
284 | 04M1024 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
285 | 04M1025 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
286 | 04M1026 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
287 | 04M1027 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
288 | 04M1028 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
289 | 04M1029 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
290 | 04M1030 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
291 | 04M1031 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
292 | 04M1032 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
293 | 04M1033 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
294 | 04M1034 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
295 | 04M1035 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
296 | 04M1036 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
297 | 04M1037 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
298 | 04M1038 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
299 | 04M1039 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
300 | 04M1040 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
301 | 04M1041 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
302 | 04M1042 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
303 | 04M1043 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
304 | 04M1044 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
305 | 04M1045 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
306 | 04M1046 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
307 | 04M1047 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
308 | 04M1048 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
309 | 04M1049 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
310 | 04M1050 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
311 | 04M1051 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
312 | 05B1000 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
313 | 05B1001 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
314 | 05B1002 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
315 | 05B1003 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
316 | 05B1004 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
317 | 05B1005 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
318 | 05B1006 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
319 | 05B1007 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
320 | 05B1008 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
321 | 05B1009 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
322 | 05B1010 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
323 | 05B1011 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
324 | 05B1012 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
325 | 05B1013 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
326 | 05B1014 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
327 | 05B1015 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
328 | 05B1016 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
329 | 05B1017 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
330 | 05B1018 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
331 | 05B1019 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
332 | 05B1020 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
333 | 05B1021 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
334 | 05C1000 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
335 | 05C1001 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
336 | 05C1002 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
337 | 05C1003 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
338 | 05C1004 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
339 | 05C1005 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
340 | 05C1006 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
341 | 05C1007 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
342 | 05C1008 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
343 | 05C1009 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
344 | 05C1010 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
345 | 05C1011 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
346 | 05C1012 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
347 | 05C1013 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
348 | 05C1014 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
349 | 05C1015 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
350 | 05C1016 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
351 | 05M1000 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
352 | 05M1001 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
353 | 05M1002 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
354 | 05M1003 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
355 | 05M1004 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
356 | 05M1005 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
357 | 05M1006 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
358 | 05M1007 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
359 | 05M1008 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
360 | 05M1009 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
361 | 05M1010 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
362 | 05M1011 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
363 | 05M1012 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
364 | 05M1013 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
365 | 05M1014 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
366 | 05M1015 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
367 | 05M1016 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
368 | 05M1017 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
369 | 05M1018 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
370 | 05M1019 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
371 | 05M1020 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
372 | 05M1021 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
373 | 05M1022 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
374 | 05M1023 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
375 | 05M1024 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
376 | 06B1000 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
377 | 06B1001 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
378 | 06B1002 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
379 | 06B1003 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
380 | 06B1004 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
381 | 06B1005 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
382 | 06B1006 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
383 | 06B1007 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
384 | 06B1008 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
385 | 06B1009 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
386 | 06B1010 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
387 | 06B1011 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
388 | 06B1012 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
389 | 06B1013 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
390 | 06B1014 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
391 | 06B1015 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
392 | 06B1016 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
393 | 06B1017 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
394 | 06B1018 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
395 | 06B1019 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
396 | 06B1020 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
397 | 06B1021 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
398 | 06B1022 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
399 | 06B1023 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
400 | 06B1024 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
401 | 06B1025 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
402 | 06B1026 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
403 | 06B1027 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
404 | 06B1028 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
405 | 06B1029 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
406 | 06B1030 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
407 | 06B1031 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
408 | 06B1032 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
409 | 06B1033 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
410 | 06B1034 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
411 | 06B1035 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
412 | 06B1036 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
413 | 06B1037 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
414 | 06B1038 | BEAM DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
415 | 06C1000 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
416 | 06C1001 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
417 | 06C1002 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
418 | 06C1003 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
419 | 06C1004 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
420 | 06C1005 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
421 | 06C1006 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
422 | 06C1007 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
423 | 06C1008 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
424 | 06C1009 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
425 | 06C1010 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
426 | 06C1011 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
427 | 06C1012 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
428 | 06C1013 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
429 | 06C1014 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
430 | 06C1015 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
431 | 06C1016 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
432 | 06C1017 | COLUMN DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
433 | 06D1000 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
434 | 06D1001 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
435 | 06D1002 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
436 | 06D1003 | VERTICAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
437 | 06D1004 | HARIZONTAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
438 | 06D1005 | HARIZONTAL BRACE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
439 | 06M1000 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
440 | 06M1001 | ANGLE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
441 | 06M1002 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
442 | 06M1003 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
443 | 06M1004 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
444 | 06M1005 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
445 | 06M1006 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
446 | 06M1007 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
447 | 06M1008 | CHANNEL DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
448 | 06M1009 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
449 | 06M1010 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
450 | 06M1011 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
451 | 06M1012 | PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
452 | 06M1013 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
453 | 06M1014 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
454 | 06M1015 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
455 | 06M1016 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
456 | 06M1017 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
457 | 06M1018 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
458 | 06M1019 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
459 | 06M1020 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
460 | 06M1021 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
461 | 06M1022 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
462 | 06M1023 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
463 | 06M1024 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
464 | 06M1025 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
465 | 06M1026 | BENT PLATE DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
466 | 06M1027 | ANGLE FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
467 | 06M1028 | FRAME DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
E-SHEETS
468 | E201 | MEZZANINE AND CANOPY FRAMING PLAN | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
469 | E202 | MEZZANINE FRAMING PLAN | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
470 | E203 | LID & LUBE ROOM FRAMING PLAN | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
471 | E204 | CANOPY FRAMING PLAN | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
472 | E205 | CRANE RUNWAY FEAMING PLAN | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
473 | E206 | ROOF FRAMING PLAN | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
474 | E207 | ROOF FRAMING PLAN | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
475 | E208 | ROOF MISC FRAMING PLAN | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
476 | E209 | ROOF MISC FRAMING PLAN | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
477 | E210 | ROOF MISC FRAMING DETAIL | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
478 | SE201 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
479 | SE202 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
480 | SE203 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
481 | SE204 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
482 | SE205 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
483 | SE206 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
484 | SE207 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
485 | SE208 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
486 | SE209 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
487 | SE210 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
488 | SE211 | ELEVATION VIEW | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
489 | SE220 | SECTIONS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
490 | SE221 | SECTION & DETAILS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
491 | SE222 | SECTION & DETAILS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
492 | SE224 | SECTIONS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
493 | SE225 | SECTIONS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
494 | SE226 | SECTIONS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
495 | SE227 | TYPICAL SECTIONS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
496 | SE228 | TYPICAL SECTIONS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
497 | SE229 | TYPICAL SECTIONS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL
498 | SE230 | TYPICAL SECTIONS | 11-06-2025 |  |  |  | ISSUED FOR APPROVAL