## Drawing Log
OUTGOING DRAWING LOG SHEET
Project Name: mm |  |  |  | Client: k
Sl. No. | Sheet No. | Drawing Title | Sent for Approval | Sent for Fabrication |  |  | Remarks
|  |  | Rev A | Rev 0 | Rev 1 | Rev 2
DRAWINGS
1 | 06M1022 | PLATE | 11-06-2025 | 28-07-2025 |  |  | ISSUED FOR APPROVAL / ISSUED FOR FABRICATION