## Drawing Log
OUTGOING DRAWING LOG SHEET
Project Name: SteelFrame | [5 empty] | Client: Infra
Sl. No. | Sheet No. | Drawing Title | Sent for Approval |  |  |  | Sent for Fabrication |  |  | Remarks
|  |  | Rev A | Rev B | Rev C | Rev LU | Rev 0 | Rev 1 | Rev 2
DRAWINGS
1 | 06D1005 | HORIZONTAL BRACE
2 | 06M1022 | BENT PLATE DETAIL | 11-06-2025 |  |  | 11-06-2025 | 28-07-2025 |  |  | ISSUED FOR FABRICATION / 2 J
3 | a15 | ANGLE |  |  |  |  | 04-11-2025 |  |  | FOR FABRICATION
4 | E-03.00 | SOW #03 -SOUTH WEST FRAMING | 02-27-2025 | 06-23-2025 | 08-22-2025 |  | 09-25-2025 |  |  | FOR CONSTRUCTION
5 | E-03.00A | SOW #03 -SOUTH WEST FRAMING |  |  |  |  | 09-25-2025 |  |  | FOR CONSTRUCTION