## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | 02B1034 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1034_0.pdf
2 | 02B1035 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1035_0.pdf
3 | 02C1012 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1012_0.pdf
4 | 02B1009 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1009_0.pdf
5 | 02B1018 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1018_0.pdf
6 | 02B1006 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1006_0.pdf
7 | 02B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1004_0.pdf
8 | 02C1003 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1003_0.pdf
9 | 02C1006 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1006_0.pdf
10 | 02B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1003_0.pdf
11 | 02C1009 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1009_0.pdf
12 | 02B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1008_0.pdf
13 | 02B1001 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1001_0.pdf
14 | 02C1001 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1001_0.pdf
15 | 02C1004 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1004_0.pdf
16 | 02C1013 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1013_0.pdf
17 | 02C1005 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1005_0.pdf
18 | 02B1007 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1007_0.pdf
19 | 02B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1005_0.pdf
20 | 02B1010 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1010_0.pdf
21 | 02C1014 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1014_0.pdf
22 | 03B1010 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1010_0.pdf
23 | 02B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1002_0.pdf
24 | 02C1011 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1011_0.pdf
25 | 03B1000 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1000_0.pdf
26 | 02C1007 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1007_0.pdf
27 | 02C1000 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1000_0.pdf
28 | 03C1000 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1000_0.pdf
29 | 03C1009 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1009_0.pdf
30 | 02C1016 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1016_0.pdf
31 | 03C1003 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1003_0.pdf
32 | 03C1012 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1012_0.pdf
33 | 03C1002 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1002_0.pdf
34 | 02C1015 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1015_0.pdf
35 | 02C1010 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1010_0.pdf
36 | 04B1010 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1010_0.pdf
37 | 03C1001 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1001_0.pdf
38 | 04B1007 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1007_0.pdf
39 | 03B1024 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1024_0.pdf
40 | 03C1015 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1015_0.pdf
41 | 02C1002 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1002_0.pdf
42 | 03C1005 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1005_0.pdf
43 | 03C1014 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1014_0.pdf
44 | 04B1011 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1011_0.pdf
45 | 03C1008 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1008_0.pdf
46 | 03C1016 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1016_0.pdf
47 | 04B1009 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1009_0.pdf
48 | 03C1011 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1011_0.pdf
49 | 03C1010 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1010_0.pdf
50 | 05B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1005_0.pdf
51 | 04B1018 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1018_0.pdf
52 | 05B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1004_0.pdf
53 | 04B1021 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1021_0.pdf
54 | 04B1017 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1017_0.pdf
55 | 03C1004 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1004_0.pdf
56 | 03C1013 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1013_0.pdf
57 | 04B1006 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1006_0.pdf
58 | 04C1001 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1001_0.pdf
59 | 04B1019 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1019_0.pdf
60 | 04C1002 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1002_0.pdf
61 | 04B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1008_0.pdf
62 | 04C1008 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1008_0.pdf
63 | 05B1006 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1006_0.pdf
64 | 05B1007 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1007_0.pdf
65 | 05B1009 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1009_0.pdf
66 | 04B1013 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1013_0.pdf
67 | 05B1021 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1021_0.pdf
68 | 05B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1008_0.pdf
69 | 05B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1016_0.pdf
70 | 04C1009 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1009_0.pdf
71 | 04C1007 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1007_0.pdf
72 | 04C1000 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1000_0.pdf
73 | 05C1012 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1012_0.pdf
74 | 05C1001 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1001_0.pdf
75 | 06B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1016_0.pdf
76 | 05C1006 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1006_0.pdf
77 | 06B1001 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1001_0.pdf
78 | 05C1010 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1010_0.pdf
79 | 06B1007 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1007_0.pdf
80 | 06B1006 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1006_0.pdf
81 | 06C1013 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1013_0.pdf
82 | 06C1012 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1012_0.pdf
83 | 06C1002 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1002_0.pdf
84 | 06C1014 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1014_0.pdf
85 | 06C1000 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1000_0.pdf
86 | 06C1008 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1008_0.pdf
87 | 05C1014 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1014_0.pdf
88 | 06B1015 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1015_0.pdf
89 | 06C1017 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1017_0.pdf
90 | 06C1011 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1011_0.pdf
91 | 06B1000 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1000_0.pdf
92 | 05C1015 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1015_0.pdf
93 | 06C1015 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1015_0.pdf
94 | 06C1010 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1010_0.pdf
95 | 06C1006 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1006_0.pdf
96 | 05C1013 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1013_0.pdf
97 | 04B1014 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1014_0.pdf
98 | 05C1016 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1016_0.pdf
99 | 06C1009 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1009_0.pdf
100 | 06C1016 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1016_0.pdf