## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | 02B1027 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1027_0.pdf
2 | 02B1028 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1028_0.pdf
3 | 02B1023 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1023_0.pdf
4 | 02B1014 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1014_0.pdf
5 | 02B1022 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1022_0.pdf
6 | 02B1030 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1030_0.pdf
7 | 02B1031 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1031_0.pdf
8 | 02B1020 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1020_0.pdf
9 | 02B1011 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1011_0.pdf
10 | 02B1040 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1040_0.pdf
11 | 02B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1016_0.pdf
12 | 02B1013 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1013_0.pdf
13 | 02B1029 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1029_0.pdf
14 | 02B1017 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1017_0.pdf
15 | 02B1025 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1025_0.pdf
16 | 02B1026 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1026_0.pdf
17 | 02B1021 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1021_0.pdf
18 | 02B1012 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1012_0.pdf
19 | 02B1037 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1037_0.pdf
20 | 02B1032 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1032_0.pdf
21 | 02B1033 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1033_0.pdf
22 | 02B1015 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1015_0.pdf
23 | 02B1036 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1036_0.pdf
24 | 02B1024 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1024_0.pdf
25 | 02B1019 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1019_0.pdf
26 | 02D1000 | ASSEMBLY | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1000_0.pdf
27 | 02B1041 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1041_0.pdf
28 | 02C1008 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1008_0.pdf
29 | 02M1001 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1001_0.pdf
30 | 02M1003 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1003_0.pdf
31 | 02M1002 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1002_0.pdf
32 | 02D1002 | ASSEMBLY | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1002_0.pdf
33 | 02D1001 | ASSEMBLY | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1001_0.pdf
34 | 02M1004 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1004_0.pdf
35 | 02M1005 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1005_0.pdf
36 | 02M1007 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1007_0.pdf
37 | 02M1006 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1006_0.pdf
38 | 02M1010 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1010_0.pdf
39 | 02M1008 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1008_0.pdf
40 | 02D1003 | ASSEMBLY | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1003_0.pdf
41 | 02M1000 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1000_0.pdf
42 | 02D1004 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1004_0.pdf
43 | 02M1009 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1009_0.pdf
44 | 02M1011 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1011_0.pdf
45 | 02M1013 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1013_0.pdf
46 | 02D1005 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1005_0.pdf
47 | 02M1014 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1014_0.pdf
48 | 02D1011 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1011_0.pdf
49 | 02D1007 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1007_0.pdf
50 | 02D1009 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1009_0.pdf
51 | 02D1008 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1008_0.pdf
52 | 02D1010 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1010_0.pdf
53 | 02D1006 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1006_0.pdf
54 | 02M1018 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1018_0.pdf
55 | 02M1015 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1015_0.pdf
56 | 02M1017 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1017_0.pdf
57 | 02M1016 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1016_0.pdf
58 | 02M1019 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1019_0.pdf
59 | 02M1020 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1020_0.pdf
60 | 02M1021 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1021_0.pdf
61 | 02M1022 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1022_0.pdf
62 | 02M1023 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1023_0.pdf
63 | 02M1024 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1024_0.pdf
64 | 02M1025 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1025_0.pdf
65 | 02M1026 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1026_0.pdf
66 | 02M1027 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1027_0.pdf
67 | 02M1028 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1028_0.pdf
68 | 02M1029 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1029_0.pdf
69 | 02M1032 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1032_0.pdf
70 | 02M1030 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1030_0.pdf
71 | 02M1034 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1034_0.pdf
72 | 02M1031 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1031_0.pdf
73 | 02M1033 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1033_0.pdf
74 | 02M1036 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1036_0.pdf
75 | 02M1037 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1037_0.pdf
76 | 02M1038 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1038_0.pdf
77 | 02M1035 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1035_0.pdf
78 | 02M1039 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1039_0.pdf
79 | 03B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1002_0.pdf
80 | 03B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1004_0.pdf
81 | 03B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1003_0.pdf
82 | 03B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1005_0.pdf
83 | 03B1011 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1011_0.pdf
84 | 03B1012 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1012_0.pdf
85 | 03B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1008_0.pdf
86 | 03B1013 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1013_0.pdf
87 | 03B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1016_0.pdf
88 | 03B1014 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1014_0.pdf
89 | 03B1018 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1018_0.pdf
90 | 03B1015 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1015_0.pdf
91 | 03B1020 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1020_0.pdf
92 | 03B1019 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1019_0.pdf
93 | 03B1017 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1017_0.pdf
94 | 03B1021 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1021_0.pdf
95 | 03B1030 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1030_0.pdf
96 | 03B1027 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1027_0.pdf
97 | 03B1022 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1022_0.pdf
98 | 03B1023 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1023_0.pdf
99 | 03B1029 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1029_0.pdf
100 | 03B1028 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1028_0.pdf
101 | 03B1026 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1026_0.pdf
102 | 03B1025 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1025_0.pdf
103 | 03B1031 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1031_0.pdf
104 | 03B1032 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1032_0.pdf
105 | 03B1034 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1034_0.pdf
106 | 03B1033 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1033_0.pdf
107 | 03B1035 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1035_0.pdf
108 | 03B1037 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1037_0.pdf
109 | 03B1045 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1045_0.pdf
110 | 03B1047 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1047_0.pdf
111 | 03B1036 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1036_0.pdf
112 | 03B1048 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1048_0.pdf
113 | 03B1051 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1051_0.pdf
114 | 03B1050 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1050_0.pdf
115 | 03B1044 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1044_0.pdf
116 | 03B1046 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1046_0.pdf
117 | 03B1042 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1042_0.pdf
118 | 03D1000 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1000_0.pdf
119 | 03B1049 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1049_0.pdf
120 | 03M1004 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1004_0.pdf
121 | 03D1001 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1001_0.pdf
122 | 03M1000 | BACK | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1000_0.pdf
123 | 03D1005 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1005_0.pdf
124 | 03D1004 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1004_0.pdf
125 | 03D1003 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1003_0.pdf
126 | 03D1002 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1002_0.pdf
127 | 03M1001 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1001_0.pdf
128 | 03M1005 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1005_0.pdf
129 | 03B1052 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1052_0.pdf
130 | 03M1008 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1008_0.pdf
131 | 03M1009 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1009_0.pdf
132 | 03M1010 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1010_0.pdf
133 | 03M1011 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1011_0.pdf
134 | 03M1016 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1016_0.pdf
135 | 03M1012 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1012_0.pdf
136 | 03M1014 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1014_0.pdf
137 | 03M1021 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1021_0.pdf
138 | 03M1017 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1017_0.pdf
139 | 03M1018 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1018_0.pdf
140 | 03M1015 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1015_0.pdf
141 | 03M1013 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1013_0.pdf
142 | 03M1020 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1020_0.pdf
143 | 03M1019 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1019_0.pdf
144 | 03M1025 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1025_0.pdf
145 | 03M1032 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1032_0.pdf
146 | 03M1028 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1028_0.pdf
147 | 03M1027 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1027_0.pdf
148 | 03M1024 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1024_0.pdf
149 | 03M1031 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1031_0.pdf
150 | 03M1029 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1029_0.pdf
151 | 03M1026 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1026_0.pdf
152 | 04B1001 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1001_0.pdf
153 | 03M1023 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1023_0.pdf
154 | 04B1000 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1000_0.pdf
155 | 03M1030 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1030_0.pdf
156 | 03M1022 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1022_0.pdf
157 | 04B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1003_0.pdf
158 | 04B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1002_0.pdf
159 | 04B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1004_0.pdf
160 | 04B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1005_0.pdf
161 | 04D1000 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1000_0.pdf
162 | 04D1002 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1002_0.pdf
163 | 04M1000 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1000_0.pdf
164 | 04M1001 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1001_0.pdf
165 | 04B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1016_0.pdf
166 | 04M1003 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1003_0.pdf
167 | 04M1004 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1004_0.pdf
168 | 04M1012 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1012_0.pdf
169 | 04D1001 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1001_0.pdf
170 | 04B1015 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1015_0.pdf
171 | 04M1002 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1002_0.pdf
172 | 04D1004 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1004_0.pdf
173 | 04M1013 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1013_0.pdf
174 | 04M1014 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1014_0.pdf
175 | 04M1008 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1008_0.pdf
176 | 04M1005 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1005_0.pdf
177 | 04M1010 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1010_0.pdf
178 | 04D1005 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1005_0.pdf
179 | 04D1003 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1003_0.pdf
180 | 04M1007 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1007_0.pdf
181 | 04M1006 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1006_0.pdf
182 | 04M1015 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1015_0.pdf
183 | 04M1016 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1016_0.pdf
184 | 04M1009 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1009_0.pdf
185 | 04M1018 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1018_0.pdf
186 | 04M1017 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1017_0.pdf
187 | 04M1022 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1022_0.pdf
188 | 04M1020 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1020_0.pdf
189 | 04M1019 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1019_0.pdf
190 | 04M1021 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1021_0.pdf
191 | 04M1023 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1023_0.pdf
192 | 04M1027 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1027_0.pdf
193 | 04M1028 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1028_0.pdf
194 | 04M1033 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1033_0.pdf
195 | 04M1026 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1026_0.pdf
196 | 04M1025 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1025_0.pdf
197 | 04M1029 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1029_0.pdf
198 | 04M1030 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1030_0.pdf
199 | 04M1031 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1031_0.pdf
200 | 04M1041 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1041_0.pdf
201 | 04M1034 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1034_0.pdf
202 | 04M1032 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1032_0.pdf
203 | 04M1040 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1040_0.pdf
204 | 04M1038 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1038_0.pdf
205 | 04M1043 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1043_0.pdf
206 | 04M1045 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1045_0.pdf
207 | 04M1039 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1039_0.pdf
208 | 04M1035 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1035_0.pdf
209 | 04M1042 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1042_0.pdf
210 | 04M1037 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1037_0.pdf
211 | 04M1044 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1044_0.pdf
212 | 04M1047 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1047_0.pdf
213 | 04M1048 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1048_0.pdf
214 | 04M1046 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1046_0.pdf
215 | 04M1052 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1052_0.pdf
216 | 04M1053 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1053_0.pdf
217 | 04M1055 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1055_0.pdf
218 | 04M1054 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1054_0.pdf
219 | 04M1058 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1058_0.pdf
220 | 04M1057 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1057_0.pdf
221 | 04M1056 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1056_0.pdf
222 | 04M1060 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1060_0.pdf
223 | 04M1061 | HSS DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1061_0.pdf
224 | 05B1000 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1000_0.pdf
225 | 05M1004 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1004_0.pdf
226 | 04M1059 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1059_0.pdf
227 | 05M1002 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1002_0.pdf
228 | 05M1011 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1011_0.pdf
229 | 05M1001 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1001_0.pdf
230 | 05M1010 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1010_0.pdf
231 | 05B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1002_0.pdf
232 | 05M1012 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1012_0.pdf
233 | 05B1001 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1001_0.pdf
234 | 05B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1003_0.pdf
235 | 05M1003 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1003_0.pdf
236 | 05M1013 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1013_0.pdf
237 | 05M1014 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1014_0.pdf
238 | 05M1015 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1015_0.pdf
239 | 05M1000 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1000_0.pdf
240 | 05M1005 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1005_0.pdf
241 | 05C1011 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1011_0.pdf
242 | 05M1016 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1016_0.pdf
243 | 05M1017 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1017_0.pdf
244 | 05M1018 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1018_0.pdf
245 | 05M1019 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1019_0.pdf
246 | 05M1020 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1020_0.pdf
247 | 05M1022 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1022_0.pdf
248 | 05M1023 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1023_0.pdf
249 | 05M1021 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1021_0.pdf
250 | 05M1025 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1025_0.pdf
251 | 05M1024 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1024_0.pdf
252 | 06B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1002_0.pdf
253 | 06B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1003_0.pdf
254 | 06B1013 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1013_0.pdf
255 | 06B1011 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1011_0.pdf
256 | 06B1009 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1009_0.pdf
257 | 06B1010 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1010_0.pdf
258 | 06B1012 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1012_0.pdf
259 | 06B1014 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1014_0.pdf
260 | 06B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1008_0.pdf
261 | 06B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1005_0.pdf
262 | 06B1035 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1035_0.pdf
263 | 06B1030 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1030_0.pdf
264 | 06B1025 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1025_0.pdf
265 | 06B1028 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1028_0.pdf
266 | 06B1033 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1033_0.pdf
267 | 06B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1004_0.pdf
268 | 06B1034 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1034_0.pdf
269 | 06B1037 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1037_0.pdf
270 | 06B1036 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1036_0.pdf
271 | 06B1038 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1038_0.pdf
272 | 06D1001 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1001_0.pdf
273 | 06D1004 | DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1004_0.pdf
274 | 06D1005 | DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1005_0.pdf
275 | 06D1003 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1003_0.pdf
276 | 06D1000 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1000_0.pdf
277 | 06M1001 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1001_0.pdf
278 | 06D1002 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1002_0.pdf
279 | 06M1002 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1002_0.pdf
280 | 06M1000 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1000_0.pdf
281 | 06M1004 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1004_0.pdf
282 | 06M1016 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1016_0.pdf
283 | 06M1020 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1020_0.pdf
284 | 06M1008 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1008_0.pdf
285 | 06M1006 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1006_0.pdf
286 | 06M1018 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1018_0.pdf
287 | 06M1013 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1013_0.pdf
288 | 06M1014 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1014_0.pdf
289 | 06M1022 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1022_0.pdf
290 | 06M1017 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1017_0.pdf
291 | 06M1005 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1005_0.pdf
292 | 06M1015 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1015_0.pdf
293 | 06M1007 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1007_0.pdf
294 | 06M1021 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1021_0.pdf
295 | 06M1003 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1003_0.pdf
296 | 06M1019 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1019_0.pdf
297 | 06M1024 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1024_0.pdf
298 | 06M1023 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1023_0.pdf
299 | 06M1026 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1026_0.pdf
300 | 06M1025 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1025_0.pdf
301 | 06M1030 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1030_0.pdf
302 | 06M1031 | HSS DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1031_0.pdf
303 | 06M1027 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1027_0.pdf
304 | 06M1028 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1028_0.pdf
305 | 06M1032 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1032_0.pdf
306 | 06M1029 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1029_0.pdf