## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | E-03.00 | BEAM | 0 | 09-25-2025 | For Construction | E-03.00_0.pdf
2 | E-03.00A | COLUMN | 0 | 09-25-2025 | For Construction | E-03.00A_0.pdf
3 | E-03.01 | PLATE | 0 | 09-25-2025 | For Construction | E-03.01_0.pdf
4 | E-03.01E | PLATE | 0 | 08-22-2025 | For Construction 09-25-2025 1 A For Approval | E-03.01E_0.pdf
5 | E-03.01A | BEAM | 0 | 09-25-2025 | For Construction | E-03.01A_0.pdf
6 | E-03.01D | PLATE | 0 | 09-25-2025 | For Construction | E-03.01D_0.pdf
7 | E-03.03 | PLATE | 0 | 08-22-2025 | For Construction 09-25-2025 3 C For Re-Approval | E-03.03_0.pdf
8 | E-03.01F | BEAM | 0 | 09-25-2025 | For Construction | E-03.01F_0.pdf
9 | E-03.01B | BEAM | 0 | 09-25-2025 | For Construction | E-03.01B_0.pdf
10 | E-03.01C | PLATE | 0 | 09-25-2025 | For Construction | E-03.01C_0.pdf
11 | E-03.05 | BEAM DETAIL | 0 | 09-25-2025 | For Construction | E-03.05_0.pdf
12 | E-03.07 | COLUMN | 0 | 09-25-2025 | For Construction | E-03.07_0.pdf
13 | E-03.04 | BEAM | 0 | 09-25-2025 | For Construction | E-03.04_0.pdf
14 | E-03.09 | COLUMN | 0 | 09-25-2025 | For Construction | E-03.09_0.pdf
15 | E-03.02 | PLATE | 0 | 09-25-2025 | For Construction | E-03.02_0.pdf
16 | E-03.06 | COLUMN | 0 | 09-25-2025 | For Construction | E-03.06_0.pdf
17 | E-03.08 | COLUMN | 0 | 09-25-2025 | For Construction | E-03.08_0.pdf
18 | E-03.10 | COLUMN | 0 | 09-25-2025 | For Construction | E-03.10_0.pdf