## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | 07M1005 | ANGLE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1005_A.pdf
2 | 07M1004 | ANGLE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1004_A.pdf
3 | 07M1002 | PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1002_A.pdf
4 | 07M1001 | PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1001_A.pdf
5 | 07M1000 | PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1000_A.pdf
6 | 07B1000 | BEAM DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07B1000_A.pdf
7 | 07M1003 | PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1003_A.pdf
8 | 07B1001 | BEAM DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07B1001_A.pdf
9 | 07GR1000 | MISCELLANEOUS | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1000_A.pdf
10 | 07C1001 | COLUMN DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07C1001_A.pdf
11 | 07C1000 | COLUMN DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07C1000_A.pdf
12 | 07M1006 | MISCELLANEOUS | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1006_A.pdf
13 | 07GR1001 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1001_A.pdf
14 | 07STR1000 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1000_A.pdf
15 | 07GR1006 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1006_A.pdf
16 | 07WR1001 | WALLRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07WR1001_A.pdf
17 | 07WR1000 | WALLRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07WR1000_A.pdf
18 | 07GR1008 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1008_A.pdf
19 | 07GR1012 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1012_A.pdf
20 | 07GR1009 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1009_A.pdf
21 | 07GR1005 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1005_A.pdf
22 | 07GR1002 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1002_A.pdf
23 | 07GR1007 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1007_A.pdf
24 | 07GR1010 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1010_A.pdf
25 | 07GR1011 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1011_A.pdf
26 | 07STR1001 | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1001_A.pdf
27 | 07FR1000 | GATE FRAME | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1000_A.pdf
28 | 07GR1004 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1004_A.pdf
29 | 07FR1003 | FRAME DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1003_A.pdf
30 | 07FR1001 | GATE FRAME | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1001_A.pdf
31 | 07STR1002 | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1002_A.pdf
32 | 07GR1003 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1003_A.pdf
33 | 07STR1001A | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1001A_A.pdf
34 | 07STR1000B | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1000B_A.pdf
35 | 07STR1000A | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1000A_A.pdf
36 | 07STR1002B | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1002B_A.pdf
37 | 07LDR1000 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL HOLES : 13/16 " DIA (U.N.O) | 07LDR1000_A.pdf
38 | 07STR1002A | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1002A_A.pdf
39 | 07STR1001B | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1001B_A.pdf
40 | 07LDR1001 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07LDR1001_A.pdf
41 | 07LDR1002 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07LDR1002_A.pdf
42 | 07FR1002 | FRAME DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1002_A.pdf