## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | bp1001 | BASE PLATE | 0 | 09-22-2025 | FOR FABRICATION | bp1001_0.pdf
2 | a738 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a738_0.pdf
3 | pl1550 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl1550_0.pdf
4 | pl2938 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED | pl2938_1.pdf
5 | pl3738 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED | pl3738_1.pdf
6 | bp1000 | BASE PLATE | 0 |  |  | bp1000_0.pdf
7 | pl1608 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl1608_0.pdf
8 | a1136 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a1136_0.pdf
9 | cp1000 | CAP PLATE | 0 | 09-22-2025 | FOR FABRICATION | cp1000_0.pdf
10 | pl3732 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3732_0.pdf
11 | a1095 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a1095_0.pdf
12 | pl3739 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3739_0.pdf
13 | a3514 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a3514_0.pdf
14 | pl3740 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3740_0.pdf
15 | pl462 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl462_0.pdf
16 | pl3749 | PLATE | 0 | 09-25-2025 | FOR FABRICATION | pl3749_0.pdf
17 | a2573 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a2573_0.pdf
18 | pl472 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl472_0.pdf
19 | pl3057 | PLATE | 0 |  |  | pl3057_0.pdf
20 | pl470 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED | pl470_1.pdf
21 | pl1517 | PLATE | 0 |  |  | pl1517_0.pdf
22 | pl3056 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3056_0.pdf
23 | pl3742 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3742_0.pdf
24 | bpl1994 | BENT PLATE | 0 | 09-22-2025 | FOR FABRICATION | bpl1994_0.pdf
25 | pl665 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl665_0.pdf
26 | pl658 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl658_0.pdf
27 | pl473 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl473_0.pdf
28 | E-03.00 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.00_0.pdf
29 | pl680 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl680_0.pdf
30 | cp1001 | CAP PLATE | 2 | 09-25-2025 | REVISED AS NOTED | cp1001_2.pdf
31 | E-03.00A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.00A_0.pdf
32 | E-03.01E | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction | E-03.01E_0.pdf
33 | E-03.01 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.01_0.pdf
34 | E-03.01A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.01A_0.pdf
35 | E-03.01D | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction | E-03.01D_0.pdf
36 | E-03.01C | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction | E-03.01C_0.pdf
37 | E-03.01B | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.01B_0.pdf
38 | E-03.01F | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction | E-03.01F_0.pdf
39 | E-03.03 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction | E-03.03_0.pdf
40 | F-03.00 | PLATE DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.00_1.pdf
41 | E-03.05 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.05_0.pdf
42 | E-03.07 | SOW #03 -SOUTH WEST FRAMING SECTIONS Scale VARIES TUORG KNIRHS-NON | 0 | 09-25-2025 | For Construction | E-03.07_0.pdf
43 | F-03.11 | MISCELLANEOUS DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.11_1.pdf
44 | E-03.02 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction | E-03.02_0.pdf
45 | E-03.04 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction | E-03.04_0.pdf
46 | F-03.09 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.09_0.pdf
47 | E-03.09 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.09_0.pdf
48 | E-03.06 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.06_0.pdf
49 | F-03.12 | MISCELLANEOUS DETAIL | 2 | 09-25-2025 | Revised as noted | F-03.12_2.pdf
50 | F-03.05 | COLUMN & BEAM DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.05_1.pdf
51 | F-03.07 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.07_0.pdf
52 | F-03.08 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.08_0.pdf
53 | F-03.06 | BEAM DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.06_1.pdf
54 | F-03.01 | COLUMN DETAIL | 2 | 09-25-2025 | Revised as noted | F-03.01_2.pdf
55 | F-03.04 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.04_0.pdf
56 | F-03.03 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.03_0.pdf
57 | E-03.08 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.08_0.pdf
58 | F-03.02 | COLUMN DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.02_1.pdf
59 | E-03.10 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.10_0.pdf
60 | pl3742 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3742_0.pdf
61 | pl3749 | PLATE | 0 | 09-25-2025 | FOR FABRICATION | pl3749_0.pdf
62 | pl473 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl473_0.pdf
63 | pl665 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl665_0.pdf
64 | pl470 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED | pl470_1.pdf
65 | pl1608 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl1608_0.pdf
66 | pl3739 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3739_0.pdf
67 | pl1517 | PLATE | 0 |  |  | pl1517_0.pdf
68 | pl1550 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl1550_0.pdf
69 | pl3740 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3740_0.pdf
70 | pl462 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl462_0.pdf
71 | bp1000 | BASE PLATE | 0 |  |  | bp1000_0.pdf
72 | pl658 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl658_0.pdf
73 | pl3057 | PLATE | 0 |  |  | pl3057_0.pdf
74 | pl3056 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3056_0.pdf
75 | pl2938 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED | pl2938_1.pdf
76 | a1136 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a1136_0.pdf
77 | a3514 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a3514_0.pdf
78 | a1095 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a1095_0.pdf
79 | a2573 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a2573_0.pdf
80 | a738 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a738_0.pdf
81 | pl472 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl472_0.pdf
82 | pl3732 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3732_0.pdf
83 | pl3738 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED | pl3738_1.pdf
84 | pl680 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl680_0.pdf
85 | bp1001 | BASE PLATE | 0 | 09-22-2025 | FOR FABRICATION | bp1001_0.pdf
86 | bpl1994 | BENT PLATE | 0 | 09-22-2025 | FOR FABRICATION | bpl1994_0.pdf
87 | cp1000 | CAP PLATE | 0 | 09-22-2025 | FOR FABRICATION | cp1000_0.pdf
88 | cp1001 | CAP PLATE | 2 | 09-25-2025 | REVISED AS NOTED | cp1001_2.pdf
89 | pl3732 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3732_0.pdf
90 | pl1608 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl1608_0.pdf
91 | pl3739 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3739_0.pdf
92 | pl3740 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3740_0.pdf
93 | pl1550 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl1550_0.pdf
94 | pl472 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl472_0.pdf
95 | pl1517 | PLATE | 0 |  |  | pl1517_0.pdf
96 | pl3738 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED | pl3738_1.pdf
97 | pl3742 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3742_0.pdf
98 | pl2938 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED | pl2938_1.pdf
99 | a738 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a738_0.pdf
100 | pl3056 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl3056_0.pdf
101 | a1095 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a1095_0.pdf
102 | a3514 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a3514_0.pdf
103 | pl473 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl473_0.pdf
104 | pl470 | PLATE | 1 | 09-25-2025 | REVISED AS NOTED | pl470_1.pdf
105 | pl665 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl665_0.pdf
106 | pl3749 | PLATE | 0 | 09-25-2025 | FOR FABRICATION | pl3749_0.pdf
107 | pl462 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl462_0.pdf
108 | pl680 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl680_0.pdf
109 | pl3057 | PLATE | 0 |  |  | pl3057_0.pdf
110 | a2573 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a2573_0.pdf
111 | a1136 | ANGLE | 0 | 09-22-2025 | FOR FABRICATION | a1136_0.pdf
112 | pl658 | PLATE | 0 | 09-22-2025 | FOR FABRICATION | pl658_0.pdf
113 | bp1000 | BASE PLATE | 0 |  |  | bp1000_0.pdf
114 | bp1001 | BASE PLATE | 0 | 09-22-2025 | FOR FABRICATION | bp1001_0.pdf
115 | bpl1994 | BENT PLATE | 0 | 09-22-2025 | FOR FABRICATION | bpl1994_0.pdf
116 | cp1000 | CAP PLATE | 0 | 09-22-2025 | FOR FABRICATION | cp1000_0.pdf
117 | E-03.00A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.00A_0.pdf
118 | E-03.00 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.00_0.pdf
119 | E-03.01E | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction | E-03.01E_0.pdf
120 | E-03.01 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.01_0.pdf
121 | cp1001 | CAP PLATE | 2 | 09-25-2025 | REVISED AS NOTED | cp1001_2.pdf
122 | E-03.01D | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction | E-03.01D_0.pdf
123 | E-03.01A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.01A_0.pdf
124 | E-03.01F | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction | E-03.01F_0.pdf
125 | E-03.01B | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.01B_0.pdf
126 | E-03.01C | SOW #03 -SOUTH WEST MISC | 0 | 09-25-2025 | For Construction | E-03.01C_0.pdf
127 | E-03.03 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction | E-03.03_0.pdf
128 | F-03.00 | PLATE DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.00_1.pdf
129 | E-03.05 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.05_0.pdf
130 | E-03.07 | SOW #03 -SOUTH WEST FRAMING SECTIONS Scale VARIES TUORG KNIRHS-NON | 0 | 09-25-2025 | For Construction | E-03.07_0.pdf
131 | E-03.04 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction | E-03.04_0.pdf
132 | E-03.02 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 0 | 09-25-2025 | For Construction | E-03.02_0.pdf
133 | E-03.09 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.09_0.pdf
134 | F-03.09 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.09_0.pdf
135 | F-03.11 | MISCELLANEOUS DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.11_1.pdf
136 | E-03.06 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.06_0.pdf
137 | F-03.12 | MISCELLANEOUS DETAIL | 2 | 09-25-2025 | Revised as noted | F-03.12_2.pdf
138 | F-03.05 | COLUMN & BEAM DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.05_1.pdf
139 | F-03.07 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.07_0.pdf
140 | F-03.06 | BEAM DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.06_1.pdf
141 | F-03.08 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.08_0.pdf
142 | F-03.01 | COLUMN DETAIL | 2 | 09-25-2025 | Revised as noted | F-03.01_2.pdf
143 | F-03.04 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.04_0.pdf
144 | F-03.03 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.03_0.pdf
145 | F-03.02 | COLUMN DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.02_1.pdf
146 | E-03.10 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.10_0.pdf