## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | SE211 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE211_A.pdf
2 | E209 | ROOF MISC FRAMING PLAN | A | 11-06-2025 | ISSUED FOR APPROVAL | E209_A.pdf
3 | E210 | ROOF MISC FRAMING DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | E210_A.pdf
4 | SE226 | SECTIONS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE226_A.pdf
5 | SE201 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE201_A.pdf
6 | SE225 | SECTIONS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE225_A.pdf
7 | SE224 | SECTIONS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE224_A.pdf
8 | SE227 | TYPICAL SECTIONS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE227_A.pdf
9 | E201 | MEZZANINE AND CANOPY FRAMING PLAN | A | 11-06-2025 | ISSUED FOR APPROVAL | E201_A.pdf
10 | E206 | ROOF FRAMING PLAN | A | 11-06-2025 | ISSUED FOR APPROVAL | E206_A.pdf
11 | 02B1011 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1011_A.pdf
12 | SE228 | TYPICAL SECTIONS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE228_A.pdf
13 | E203 | LID & LUBE ROOM FRAMING PLAN | A | 11-06-2025 | ISSUED FOR APPROVAL | E203_A.pdf
14 | 02B1012 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1012_A.pdf
15 | 02B1013 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1013_A.pdf
16 | 02B1014 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1014_A.pdf
17 | 02B1015 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1015_A.pdf
18 | 02B1016 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1016_A.pdf
19 | SE205 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE205_A.pdf
20 | 02B1017 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1017_A.pdf
21 | SE202 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE202_A.pdf
22 | SE220 | SECTIONS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE220_A.pdf
23 | SE203 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE203_A.pdf
24 | E202 | MEZZANINE FRAMING PLAN | A | 11-06-2025 | ISSUED FOR APPROVAL | E202_A.pdf
25 | SE208 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE208_A.pdf
26 | SE209 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE209_A.pdf
27 | SE206 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE206_A.pdf
28 | SE230 | TYPICAL SECTIONS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE230_A.pdf
29 | SE229 | TYPICAL SECTIONS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE229_A.pdf
30 | SE222 | SECTION & DETAILS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE222_A.pdf
31 | E205 | CRANE RUNWAY FEAMING PLAN | A | 11-06-2025 | ISSUED FOR APPROVAL | E205_A.pdf
32 | SE221 | SECTION & DETAILS | A | 11-06-2025 | ISSUED FOR APPROVAL | SE221_A.pdf
33 | 02B1020 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1020_A.pdf
34 | 02B1022 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1022_A.pdf
35 | 02B1024 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1024_A.pdf
36 | 02B1023 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1023_A.pdf
37 | 02B1025 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1025_A.pdf
38 | 02B1019 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1019_A.pdf
39 | 02B1021 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1021_A.pdf
40 | 02B1027 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1027_A.pdf
41 | 02B1026 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1026_A.pdf
42 | 02B1028 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1028_A.pdf
43 | E207 | ROOF FRAMING PLAN | A | 11-06-2025 | ISSUED FOR APPROVAL | E207_A.pdf
44 | 02B1029 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1029_A.pdf
45 | 02B1030 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1030_A.pdf
46 | 02B1031 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1031_A.pdf
47 | 02B1033 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1033_A.pdf
48 | 02B1032 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1032_A.pdf
49 | SE207 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE207_A.pdf
50 | SE210 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE210_A.pdf
51 | 02B1037 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1037_A.pdf
52 | 02B1036 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1036_A.pdf
53 | 02B1040 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1040_A.pdf
54 | 02B1041 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1041_A.pdf
55 | 02B1007 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1007_A.pdf
56 | 02B1018 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1018_A.pdf
57 | SE204 | ELEVATION VIEW | A | 11-06-2025 | ISSUED FOR APPROVAL | SE204_A.pdf
58 | 02B1005 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1005_A.pdf
59 | 02B1008 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1008_A.pdf
60 | 02B1035 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1035_A.pdf
61 | 02B1034 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1034_A.pdf
62 | 02C1005 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1005_A.pdf
63 | 02C1006 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1006_A.pdf
64 | 02B1001 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1001_A.pdf
65 | 02C1007 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1007_A.pdf
66 | 02B1038 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1038_A.pdf
67 | 02B1039 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1039_A.pdf
68 | E208 | ROOF MISC FRAMING PLAN | A | 11-06-2025 | ISSUED FOR APPROVAL | E208_A.pdf
69 | 02B1042 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1042_A.pdf
70 | 02B1006 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1006_A.pdf
71 | 02B1003 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1003_A.pdf
72 | 02B1009 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1009_A.pdf
73 | 02B1010 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1010_A.pdf
74 | 02C1008 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1008_A.pdf
75 | 02D1000 | HORIZONTAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1000_A.pdf
76 | 02D1001 | HORIZONTAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1001_A.pdf
77 | 02D1002 | HORIZONTAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1002_A.pdf
78 | 02D1003 | HORIZONTAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1003_A.pdf
79 | 02D1004 | VERTICAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1004_A.pdf
80 | 02B1004 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1004_A.pdf
81 | 02D1005 | VERTICAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1005_A.pdf
82 | 02D1007 | VERTICAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1007_A.pdf
83 | 02D1006 | VERTICAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1006_A.pdf
84 | 02D1009 | VERTICAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1009_A.pdf
85 | 02B1000 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1000_A.pdf
86 | 02D1008 | VERTICAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1008_A.pdf
87 | 02D1010 | VERTICAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1010_A.pdf
88 | 02B1046 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1046_A.pdf
89 | 02M1000 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1000_A.pdf
90 | 02D1011 | VERTICAL BRACE | A | 11-06-2025 | ISSUED FOR APPROVAL | 02D1011_A.pdf
91 | 02M1002 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1002_A.pdf
92 | 02M1001 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1001_A.pdf
93 | 02M1003 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1003_A.pdf
94 | 02B1045 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1045_A.pdf
95 | 02M1004 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1004_A.pdf
96 | 02M1005 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1005_A.pdf
97 | 02M1007 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1007_A.pdf
98 | 02M1006 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1006_A.pdf
99 | 02B1043 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1043_A.pdf
100 | 02M1008 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1008_A.pdf
101 | 02M1010 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1010_A.pdf
102 | 02M1009 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1009_A.pdf
103 | 02M1012 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1012_A.pdf
104 | 02M1013 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1013_A.pdf
105 | 02M1011 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1011_A.pdf
106 | 02M1014 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1014_A.pdf
107 | 02M1016 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1016_A.pdf
108 | 02M1017 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1017_A.pdf
109 | 02M1015 | 02M1015 ONE ANGLE FRAME 178 178 | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1015_A.pdf
110 | 02M1018 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1018_A.pdf
111 | 02M1019 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1019_A.pdf
112 | 02M1020 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1020_A.pdf
113 | 02M1022 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1022_A.pdf
114 | 02M1026 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1026_A.pdf
115 | 02M1024 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1024_A.pdf
116 | 02M1023 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1023_A.pdf
117 | 02M1021 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1021_A.pdf
118 | 02M1025 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1025_A.pdf
119 | 02C1009 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1009_A.pdf
120 | 02M1027 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1027_A.pdf
121 | 02M1028 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1028_A.pdf
122 | 02M1029 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1029_A.pdf
123 | 02M1032 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1032_A.pdf
124 | 02M1031 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1031_A.pdf
125 | 02M1033 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1033_A.pdf
126 | 02M1030 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1030_A.pdf
127 | 02M1034 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1034_A.pdf
128 | 02M1035 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02M1035_A.pdf
129 | 02B1002 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1002_A.pdf
130 | 03B1002 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1002_A.pdf
131 | 03B1004 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1004_A.pdf
132 | 02B1044 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02B1044_A.pdf
133 | 03B1003 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1003_A.pdf
134 | 03B1006 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1006_A.pdf
135 | 03B1005 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1005_A.pdf
136 | 03B1007 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1007_A.pdf
137 | 02C1015 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1015_A.pdf
138 | 03B1008 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1008_A.pdf
139 | 03B1013 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1013_A.pdf
140 | 02C1013 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1013_A.pdf
141 | 03B1009 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1009_A.pdf
142 | 03B1018 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1018_A.pdf
143 | 03B1019 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1019_A.pdf
144 | 02C1012 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1012_A.pdf
145 | 03B1015 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1015_A.pdf
146 | 03B1011 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1011_A.pdf
147 | 03B1017 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1017_A.pdf
148 | 02C1011 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1011_A.pdf
149 | 03B1016 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1016_A.pdf
150 | 02C1014 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1014_A.pdf
151 | 03B1012 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1012_A.pdf
152 | 03B1014 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1014_A.pdf
153 | 03B1023 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1023_A.pdf
154 | 02C1000 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1000_A.pdf
155 | 03B1021 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1021_A.pdf
156 | 03B1030 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1030_A.pdf
157 | 03B1026 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1026_A.pdf
158 | 03B1028 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1028_A.pdf
159 | 03B1025 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1025_A.pdf
160 | 03B1027 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1027_A.pdf
161 | 03B1031 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1031_A.pdf
162 | 03B1029 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1029_A.pdf
163 | 03B1033 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1033_A.pdf
164 | 03B1020 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1020_A.pdf
165 | 03B1032 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1032_A.pdf
166 | 03B1036 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1036_A.pdf
167 | 03B1035 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1035_A.pdf
168 | 03B1038 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1038_A.pdf
169 | 03B1022 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1022_A.pdf
170 | 03B1042 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1042_A.pdf
171 | 03B1039 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1039_A.pdf
172 | 03B1043 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1043_A.pdf
173 | 03B1046 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1046_A.pdf
174 | 03B1044 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1044_A.pdf
175 | 03B1041 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1041_A.pdf
176 | 03B1049 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1049_A.pdf
177 | 03B1047 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1047_A.pdf
178 | 03B1037 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1037_A.pdf
179 | 03B1051 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1051_A.pdf
180 | 03B1052 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1052_A.pdf
181 | 03B1050 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1050_A.pdf
182 | 03B1048 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1048_A.pdf
183 | 03B1040 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1040_A.pdf
184 | 03B1045 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1045_A.pdf
185 | 03B1034 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1034_A.pdf
186 | 03B1010 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1010_A.pdf
187 | 02C1003 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1003_A.pdf
188 | E204 | CANOPY FRAMING PLAN | A | 11-06-2025 | ISSUED FOR APPROVAL | E204_A.pdf
189 | 03B1000 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1000_A.pdf
190 | 02C1001 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1001_A.pdf
191 | 03D1000 | HORIZONTAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03D1000_A.pdf
192 | 03B1001 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1001_A.pdf
193 | 03D1001 | HORIZONTAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03D1001_A.pdf
194 | 03D1002 | HORIZONTAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03D1002_A.pdf
195 | 03D1003 | HORIZONTAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03D1003_A.pdf
196 | 03M1000 | BACKING BAR DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1000_A.pdf
197 | 02C1010 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1010_A.pdf
198 | 03C1011 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1011_A.pdf
199 | 03M1002 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1002_A.pdf
200 | 03M1001 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1001_A.pdf
201 | 03M1003 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1003_A.pdf
202 | 03M1004 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1004_A.pdf
203 | 03M1006 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1006_A.pdf
204 | 03M1005 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1005_A.pdf
205 | 03C1012 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1012_A.pdf
206 | 02C1004 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1004_A.pdf
207 | 03M1007 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1007_A.pdf
208 | 03C1014 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1014_A.pdf
209 | 03C1001 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1001_A.pdf
210 | 03B1024 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1024_A.pdf
211 | 03M1008 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1008_A.pdf
212 | 03M1009 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1009_A.pdf
213 | 03M1010 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1010_A.pdf
214 | 03C1013 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1013_A.pdf
215 | 03M1011 | HSS DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1011_A.pdf
216 | 03M1014 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1014_A.pdf
217 | 03M1015 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1015_A.pdf
218 | 03M1012 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1012_A.pdf
219 | 03M1019 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1019_A.pdf
220 | 03M1018 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1018_A.pdf
221 | 03M1020 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1020_A.pdf
222 | 03M1017 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1017_A.pdf
223 | 03M1016 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1016_A.pdf
224 | 03M1022 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1022_A.pdf
225 | 03M1023 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1023_A.pdf
226 | 03M1021 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1021_A.pdf
227 | 03M1024 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1024_A.pdf
228 | 03C1009 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1009_A.pdf
229 | 03M1025 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1025_A.pdf
230 | 03M1026 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1026_A.pdf
231 | 03M1013 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1013_A.pdf
232 | 03C1003 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1003_A.pdf
233 | 03M1027 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1027_A.pdf
234 | 03M1028 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1028_A.pdf
235 | 03M1030 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1030_A.pdf
236 | 03M1029 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03M1029_A.pdf
237 | 04B1000 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1000_A.pdf
238 | 04B1001 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1001_A.pdf
239 | 03C1017 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1017_A.pdf
240 | 04B1016 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1016_A.pdf
241 | 03C1002 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1002_A.pdf
242 | 04B1003 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1003_A.pdf
243 | 04B1004 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1004_A.pdf
244 | 04B1005 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1005_A.pdf
245 | 03C1015 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1015_A.pdf
246 | 03C1000 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1000_A.pdf
247 | 03C1016 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1016_A.pdf
248 | 04B1002 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1002_A.pdf
249 | 03C1010 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1010_A.pdf
250 | 03C1007 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1007_A.pdf
251 | 02C1002 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 02C1002_A.pdf
252 | 04B1015 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1015_A.pdf
253 | 04B1011 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1011_A.pdf
254 | 04B1025 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1025_A.pdf
255 | 03C1004 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1004_A.pdf
256 | 04B1020 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1020_A.pdf
257 | 03C1006 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1006_A.pdf
258 | 04B1019 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1019_A.pdf
259 | 04B1010 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1010_A.pdf
260 | 04B1009 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1009_A.pdf
261 | 04B1017 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1017_A.pdf
262 | 04B1012 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1012_A.pdf
263 | 04D1000 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04D1000_A.pdf
264 | 04B1021 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1021_A.pdf
265 | 04D1001 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04D1001_A.pdf
266 | 04B1022 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1022_A.pdf
267 | 04D1002 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04D1002_A.pdf
268 | 04D1003 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04D1003_A.pdf
269 | 04M1000 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1000_A.pdf
270 | 04D1004 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04D1004_A.pdf
271 | 04M1001 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1001_A.pdf
272 | 04B1013 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1013_A.pdf
273 | 04D1005 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04D1005_A.pdf
274 | 04M1002 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1002_A.pdf
275 | 04B1024 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1024_A.pdf
276 | 04M1003 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1003_A.pdf
277 | 04M1004 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1004_A.pdf
278 | 04M1005 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1005_A.pdf
279 | 04M1007 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1007_A.pdf
280 | 03C1008 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1008_A.pdf
281 | 04B1007 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1007_A.pdf
282 | 04M1008 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1008_A.pdf
283 | 04M1006 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1006_A.pdf
284 | 04M1009 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1009_A.pdf
285 | 04M1011 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1011_A.pdf
286 | 04M1010 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1010_A.pdf
287 | 04M1012 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1012_A.pdf
288 | 04M1013 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1013_A.pdf
289 | 04M1014 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1014_A.pdf
290 | 04M1015 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1015_A.pdf
291 | 04M1016 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1016_A.pdf
292 | 04M1018 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1018_A.pdf
293 | 04M1020 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1020_A.pdf
294 | 04M1021 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1021_A.pdf
295 | 04M1024 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1024_A.pdf
296 | 04M1019 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1019_A.pdf
297 | 04M1025 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1025_A.pdf
298 | 04M1022 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1022_A.pdf
299 | 03C1005 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03C1005_A.pdf
300 | 04B1008 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1008_A.pdf
301 | 04M1029 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1029_A.pdf
302 | 04M1023 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1023_A.pdf
303 | 04M1027 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1027_A.pdf
304 | 04M1026 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1026_A.pdf
305 | 04M1030 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1030_A.pdf
306 | 04M1031 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1031_A.pdf
307 | 04M1028 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1028_A.pdf
308 | 04M1032 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1032_A.pdf
309 | 04B1006 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1006_A.pdf
310 | 04C1009 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1009_A.pdf
311 | 04C1001 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1001_A.pdf
312 | 04B1014 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1014_A.pdf
313 | 04C1004 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1004_A.pdf
314 | 04M1033 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1033_A.pdf
315 | 04M1041 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1041_A.pdf
316 | 04B1018 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1018_A.pdf
317 | 04M1038 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1038_A.pdf
318 | 04M1047 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1047_A.pdf
319 | 04M1046 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1046_A.pdf
320 | 04M1035 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1035_A.pdf
321 | 04M1045 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1045_A.pdf
322 | 04M1042 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1042_A.pdf
323 | 04M1040 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1040_A.pdf
324 | 04M1036 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1036_A.pdf
325 | 04M1034 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1034_A.pdf
326 | 04M1039 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1039_A.pdf
327 | 04M1043 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1043_A.pdf
328 | 04M1044 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1044_A.pdf
329 | 04M1037 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1037_A.pdf
330 | 04B1023 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04B1023_A.pdf
331 | 04M1048 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1048_A.pdf
332 | 04C1007 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1007_A.pdf
333 | 04M1050 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1050_A.pdf
334 | 04M1051 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1051_A.pdf
335 | 04M1049 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1049_A.pdf
336 | 05B1000 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1000_A.pdf
337 | 05B1002 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1002_A.pdf
338 | 04C1005 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1005_A.pdf
339 | 04C1003 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1003_A.pdf
340 | 04C1008 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1008_A.pdf
341 | 05B1001 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1001_A.pdf
342 | 05B1003 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1003_A.pdf
343 | 04C1002 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1002_A.pdf
344 | 04C1000 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1000_A.pdf
345 | 04M1017 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04M1017_A.pdf
346 | 04C1006 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 04C1006_A.pdf
347 | 05B1004 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1004_A.pdf
348 | 05B1005 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1005_A.pdf
349 | 05B1019 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1019_A.pdf
350 | 05B1018 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1018_A.pdf
351 | 05B1016 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1016_A.pdf
352 | 05B1017 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1017_A.pdf
353 | 05B1010 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1010_A.pdf
354 | 05B1008 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1008_A.pdf
355 | 05C1011 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1011_A.pdf
356 | 05B1014 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1014_A.pdf
357 | 05B1013 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1013_A.pdf
358 | 05B1006 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1006_A.pdf
359 | 05M1000 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1000_A.pdf
360 | 05M1001 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1001_A.pdf
361 | 05B1015 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1015_A.pdf
362 | 05M1002 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1002_A.pdf
363 | 05M1003 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1003_A.pdf
364 | 05B1021 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1021_A.pdf
365 | 05C1001 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1001_A.pdf
366 | 05M1004 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1004_A.pdf
367 | 05M1005 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1005_A.pdf
368 | 05B1011 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1011_A.pdf
369 | 05M1006 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1006_A.pdf
370 | 05M1007 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1007_A.pdf
371 | 05M1008 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1008_A.pdf
372 | 05M1009 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1009_A.pdf
373 | 05M1010 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1010_A.pdf
374 | 05M1011 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1011_A.pdf
375 | 05M1012 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1012_A.pdf
376 | 05M1014 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1014_A.pdf
377 | 05M1013 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1013_A.pdf
378 | 05M1015 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1015_A.pdf
379 | 05M1016 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1016_A.pdf
380 | 05M1017 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1017_A.pdf
381 | 05M1019 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1019_A.pdf
382 | 05M1018 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1018_A.pdf
383 | 05M1020 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1020_A.pdf
384 | 05M1021 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1021_A.pdf
385 | 05B1009 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1009_A.pdf
386 | 05M1022 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1022_A.pdf
387 | 05M1023 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1023_A.pdf
388 | 05M1024 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05M1024_A.pdf
389 | 05C1010 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1010_A.pdf
390 | 05B1020 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1020_A.pdf
391 | 06B1000 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1000_A.pdf
392 | 05B1007 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1007_A.pdf
393 | 06B1002 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1002_A.pdf
394 | 05C1013 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1013_A.pdf
395 | 06B1006 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1006_A.pdf
396 | 06B1003 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1003_A.pdf
397 | 05C1006 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1006_A.pdf
398 | 06B1005 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1005_A.pdf
399 | 06B1008 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1008_A.pdf
400 | 06B1011 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1011_A.pdf
401 | 06B1004 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1004_A.pdf
402 | 06B1009 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1009_A.pdf
403 | 06B1010 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1010_A.pdf
404 | 06B1012 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1012_A.pdf
405 | 06B1013 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1013_A.pdf
406 | 05B1012 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05B1012_A.pdf
407 | 06B1014 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1014_A.pdf
408 | 05C1005 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1005_A.pdf
409 | 06B1025 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1025_A.pdf
410 | 05C1015 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1015_A.pdf
411 | 05C1012 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1012_A.pdf
412 | 06B1027 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1027_A.pdf
413 | 06B1028 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1028_A.pdf
414 | 05C1003 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1003_A.pdf
415 | 06B1001 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1001_A.pdf
416 | 06B1030 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1030_A.pdf
417 | 06B1029 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1029_A.pdf
418 | 05C1014 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1014_A.pdf
419 | 05C1002 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1002_A.pdf
420 | 06B1035 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1035_A.pdf
421 | 06B1033 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1033_A.pdf
422 | 05C1008 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1008_A.pdf
423 | 05C1016 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1016_A.pdf
424 | 06B1037 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1037_A.pdf
425 | 06B1036 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1036_A.pdf
426 | 06B1026 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1026_A.pdf
427 | 06B1034 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1034_A.pdf
428 | 06B1017 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1017_A.pdf
429 | 06B1023 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1023_A.pdf
430 | 05C1009 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1009_A.pdf
431 | 06B1015 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1015_A.pdf
432 | 06B1038 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1038_A.pdf
433 | 06B1007 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1007_A.pdf
434 | 05C1007 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1007_A.pdf
435 | 05C1000 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1000_A.pdf
436 | 06B1024 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1024_A.pdf
437 | 06B1016 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1016_A.pdf
438 | 06C1013 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1013_A.pdf
439 | 06B1020 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1020_A.pdf
440 | 06C1014 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1014_A.pdf
441 | 06D1000 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06D1000_A.pdf
442 | 05C1004 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 05C1004_A.pdf
443 | 06B1019 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1019_A.pdf
444 | 06D1001 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06D1001_A.pdf
445 | 06D1002 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06D1002_A.pdf
446 | 06D1003 | VERTICAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06D1003_A.pdf
447 | 06B1022 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1022_A.pdf
448 | 06B1032 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1032_A.pdf
449 | 06B1021 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1021_A.pdf
450 | 06C1011 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1011_A.pdf
451 | 06B1018 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1018_A.pdf
452 | 06B1031 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06B1031_A.pdf
453 | 06C1016 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1016_A.pdf
454 | 06M1005 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1005_A.pdf
455 | 06C1006 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1006_A.pdf
456 | 06M1008 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1008_A.pdf
457 | 06M1006 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1006_A.pdf
458 | 06M1007 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1007_A.pdf
459 | 06M1004 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1004_A.pdf
460 | 06M1001 | ANGLE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1001_A.pdf
461 | 06C1009 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1009_A.pdf
462 | 06D1004 | HARIZONTAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06D1004_A.pdf
463 | 06M1003 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1003_A.pdf
464 | 06D1005 | HARIZONTAL BRACE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06D1005_A.pdf
465 | 06M1000 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1000_A.pdf
466 | 06M1009 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1009_A.pdf
467 | 06M1011 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1011_A.pdf
468 | 06C1002 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1002_A.pdf
469 | 06M1012 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1012_A.pdf
470 | 06C1003 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1003_A.pdf
471 | 06M1014 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1014_A.pdf
472 | 06M1013 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1013_A.pdf
473 | 06M1010 | PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1010_A.pdf
474 | 06M1015 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1015_A.pdf
475 | 06M1019 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1019_A.pdf
476 | 06M1016 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1016_A.pdf
477 | 06C1005 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1005_A.pdf
478 | 06M1017 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1017_A.pdf
479 | 06M1002 | CHANNEL DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1002_A.pdf
480 | 06M1018 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1018_A.pdf
481 | 06M1020 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1020_A.pdf
482 | 06C1012 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1012_A.pdf
483 | 06M1021 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1021_A.pdf
484 | 06C1015 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1015_A.pdf
485 | 06C1008 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1008_A.pdf
486 | 06M1022 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1022_A.pdf
487 | 06M1024 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1024_A.pdf
488 | 06M1023 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1023_A.pdf
489 | 06C1017 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1017_A.pdf
490 | 06M1025 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1025_A.pdf
491 | 06M1026 | BENT PLATE DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1026_A.pdf
492 | 06M1027 | ANGLE FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1027_A.pdf
493 | 06C1010 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1010_A.pdf
494 | 06C1007 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1007_A.pdf
495 | 06C1004 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1004_A.pdf
496 | 06C1000 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1000_A.pdf
497 | 06C1001 | COLUMN DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06C1001_A.pdf
498 | 06M1028 | FRAME DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 06M1028_A.pdf