## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | 06M1022 | PLATE | LU | 11-06-2025 | 2 J | 06M1022_A.pdf
2 | 06M1022 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1022_0.pdf
3 | 06D1005 | HORIZONTAL BRACE | A |  |  | 06D1005_A.pdf
4 | a15 | ANGLE | 0 | 04-11-2025 | For Fabrication | a15 - ANGLE - Rev 0.pdf
5 | 06M1022 | PLATE | LU | 11-06-2025 | 2 J | 06M1022_A.pdf
6 | E-03.00A | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.00A_0.pdf
7 | E-03.00 | SOW #03 -SOUTH WEST FRAMING | 0 | 09-25-2025 | For Construction | E-03.00_0.pdf