## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | F-03.00 | PLATE DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.00_1.pdf
2 | F-03.12 | MISCELLANEOUS DETAIL | 2 | 09-25-2025 | Revised as noted | F-03.12_2.pdf
3 | F-03.09 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.09_0.pdf
4 | F-03.01 | COLUMN DETAIL | 2 | 09-25-2025 | Revised as noted | F-03.01_2.pdf
5 | F-03.11 | MISCELLANEOUS DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.11_1.pdf
6 | F-03.05 | COLUMN & BEAM DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.05_1.pdf
7 | F-03.03 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.03_0.pdf
8 | F-03.04 | COLUMN DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.04_0.pdf
9 | F-03.02 | COLUMN DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.02_1.pdf
10 | F-03.07 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.07_0.pdf
11 | F-03.08 | BEAM DETAIL | 0 | 09-22-2025 | For Fabrication | F-03.08_0.pdf
12 | F-03.06 | BEAM DETAIL | 1 | 09-25-2025 | Revised as noted | F-03.06_1.pdf
13 | 2AL47 | ANGLE | 0 | 06-26-2025 | For Fabrication GSC JUNIPER RBP PHASE-II | 2AL47 - LINTEL ANGLE - Rev 0.pdf
14 | a21 | ANGLE | 0 | 04-11-2025 | For Fabrication | a21 - ANGLE - Rev 0.pdf
15 | 07GR1012 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1012_A.pdf
16 | 07GR1000 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1000_A.pdf
17 | 07M1003 | BENT PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1003_A.pdf
18 | 07M1001 | BENT PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1001_A.pdf
19 | 07M1005 | ANGLE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1005_A.pdf
20 | 07C1000 | COLUMN DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07C1000_A.pdf
21 | 07C1001 | COLUMN DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07C1001_A.pdf
22 | 07M1004 | ANGLE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1004_A.pdf
23 | 07M1000 | CHECKERED PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1000_A.pdf
24 | 07B1001 | BEAM DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07B1001_A.pdf
25 | 07M1002 | BENT PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1002_A.pdf
26 | 07B1000 | BEAM DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07B1000_A.pdf
27 | 07M1006 | SLEEVE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1006_A.pdf
28 | 07GR1002 | GUARDRAIL DETAIL | 23 | BAR 2 1111 | rb33 23 3/4" Ø ROUND | 07GR1002_A.pdf
29 | 07GR1008 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1008_A.pdf
30 | 07FR1001 | GATE FRAME | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1001_A.pdf
31 | 07GR1011 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1011_A.pdf
32 | 07FR1003 | FRAME DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1003_A.pdf
33 | 07GR1006 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1006_A.pdf
34 | 07GR1004 | GUARDRAIL DETAIL | 4 | BAR 2 1111 | rb33 4 3/4" Ø ROUND | 07GR1004_A.pdf
35 | 07GR1010 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1010_A.pdf
36 | 07WR1001 | WALLRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07WR1001_A.pdf
37 | 07GR1012 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1012_A.pdf
38 | 07WR1000 | WALLRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07WR1000_A.pdf
39 | 07STR1001 | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1001_A.pdf
40 | 07GR1001 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1001_A.pdf
41 | 07GR1009 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1009_A.pdf
42 | 07GR1007 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1007_A.pdf
43 | 07GR1005 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1005_A.pdf
44 | 07STR1000 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1000_A.pdf
45 | 07GR1003 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1003_A.pdf
46 | 07STR1000A | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1000A_A.pdf
47 | 07STR1001B | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1001B_A.pdf
48 | 07STR1002 | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1002_A.pdf
49 | 07STR1000B | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1000B_A.pdf
50 | 07FR1002 | FRAME DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1002_A.pdf
51 | 07STR1002A | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1002A_A.pdf
52 | 07FR1000 | GATE FRAME | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1000_A.pdf
53 | 07STR1001A | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1001A_A.pdf
54 | 07LDR1002 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07LDR1002_A.pdf
55 | 07LDR1000 | LADDER DETAIL | B | 16-06-2025 | A GSV | 07LDR1000_A.pdf
56 | 07LDR1001 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07LDR1001_A.pdf
57 | 07STR1002B | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1002B_A.pdf
58 | 07GR1012 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1012_A.pdf
59 | 07M1004 | ANGLE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1004_A.pdf
60 | 07M1003 | BENT PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1003_A.pdf
61 | 07B1001 | BEAM DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07B1001_A.pdf
62 | 07C1001 | COLUMN DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07C1001_A.pdf
63 | 07C1000 | COLUMN DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07C1000_A.pdf
64 | 07M1001 | BENT PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1001_A.pdf
65 | 07M1005 | ANGLE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1005_A.pdf
66 | 07M1002 | BENT PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1002_A.pdf
67 | 07B1000 | BEAM DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07B1000_A.pdf
68 | 07GR1000 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1000_A.pdf
69 | 07M1000 | CHECKERED PLATE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1000_A.pdf
70 | 07M1006 | SLEEVE DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07M1006_A.pdf
71 | 07GR1006 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1006_A.pdf
72 | 07GR1002 | GUARDRAIL DETAIL | 23 | BAR 2 1111 | rb33 23 3/4" Ø ROUND | 07GR1002_A.pdf
73 | 07GR1001 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1001_A.pdf
74 | 07GR1008 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1008_A.pdf
75 | 07GR1007 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1007_A.pdf
76 | 07GR1012 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1012_A.pdf
77 | 07GR1009 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1009_A.pdf
78 | 07WR1001 | WALLRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07WR1001_A.pdf
79 | 07GR1003 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1003_A.pdf
80 | 07WR1000 | WALLRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07WR1000_A.pdf
81 | 07FR1003 | FRAME DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1003_A.pdf
82 | 07FR1001 | GATE FRAME | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1001_A.pdf
83 | 07STR1000 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1000_A.pdf
84 | 07FR1000 | GATE FRAME | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1000_A.pdf
85 | 07STR1001 | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1001_A.pdf
86 | 07GR1005 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1005_A.pdf
87 | 07STR1000A | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1000A_A.pdf
88 | 07GR1004 | GUARDRAIL DETAIL | 4 | BAR 2 1111 | rb33 4 3/4" Ø ROUND | 07GR1004_A.pdf
89 | 07STR1002 | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1002_A.pdf
90 | 07GR1011 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1011_A.pdf
91 | 07GR1010 | GUARDRAIL DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07GR1010_A.pdf
92 | 07LDR1001 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07LDR1001_A.pdf
93 | 07STR1002A | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1002A_A.pdf
94 | 07STR1001B | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1001B_A.pdf
95 | 07STR1001A | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1001A_A.pdf
96 | 07STR1000B | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1000B_A.pdf
97 | 07LDR1000 | LADDER DETAIL | B | 16-06-2025 | A GSV | 07LDR1000_A.pdf
98 | 07STR1002B | STAIR DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07STR1002B_A.pdf
99 | 07LDR1002 | LADDER DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07LDR1002_A.pdf
100 | 07FR1002 | FRAME DETAIL | A | 16-06-2025 | ISSUED FOR APPROVAL | 07FR1002_A.pdf