## Drawing Log
OUTGOING DRAWING LOG SHEET
Project Name : ABC |  |  |  | Client : XYZ
Sl. No | Sheet No | Drawing Title | Sent for Approval | Sent for Fabrication |  | Remarks
|  |  | Rev A | Rev 0 | Rev 3
DRAWINGS
1 | 02B1001 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
2 | 02B1002 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
3 | 02B1003 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
4 | 02B1004 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
5 | 02B1005 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
6 | 02B1006 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
7 | 02B1007 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
8 | 02B1008 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
9 | 02B1009 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
10 | 02B1010 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
11 | 02B1018 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
12 | 02B1034 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
13 | 02B1035 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
14 | 02C1000 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
15 | 02C1001 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
16 | 02C1002 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
17 | 02C1003 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
18 | 02C1004 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
19 | 02C1005 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
20 | 02C1006 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
21 | 02C1007 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
22 | 02C1009 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
23 | 02C1010 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
24 | 02C1011 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
25 | 02C1012 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
26 | 02C1013 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
27 | 02C1014 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
28 | 02C1015 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
29 | 02C1016 | COLUMN DETAIL |  | 28-07-2025 |  | ISSUED FOR FABRICATION
30 | 03B1000 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
31 | 03B1010 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
32 | 03B1024 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
33 | 03C1000 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
34 | 03C1001 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
35 | 03C1002 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
36 | 03C1003 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
37 | 03C1004 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | GSV
38 | 03C1005 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
39 | 03C1008 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 | 3-32-71 | 3
40 | 03C1009 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
41 | 03C1010 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
42 | 03C1011 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
43 | 03C1012 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
44 | 03C1013 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
45 | 03C1014 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
46 | 03C1015 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
47 | 03C1016 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
48 | 04B1006 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
49 | 04B1007 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
50 | 04B1008 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
51 | 04B1009 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
52 | 04B1010 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
53 | 04B1011 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
54 | 04B1013 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
55 | 04B1014 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
56 | 04B1017 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
57 | 04B1018 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
58 | 04B1019 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
59 | 04B1021 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
60 | 04C1000 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
61 | 04C1001 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
62 | 04C1002 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
63 | 04C1007 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
64 | 04C1008 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
65 | 04C1009 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
66 | 05B1004 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
67 | 05B1005 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
68 | 05B1006 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
69 | 05B1007 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
70 | 05B1008 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
71 | 05B1009 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
72 | 05B1016 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
73 | 05B1021 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
74 | 05C1001 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
75 | 05C1006 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
76 | 05C1010 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
77 | 05C1012 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
78 | 05C1013 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
79 | 05C1014 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
80 | 05C1015 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
81 | 05C1016 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
82 | 06B1000 | BEAM DETAIL |  | 28-07-2025 |  | ISSUED FOR FABRICATION
83 | 06B1001 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
84 | 06B1006 | BEAM DETAIL |  | 28-07-2025 |  | ISSUED FOR FABRICATION
85 | 06B1007 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
86 | 06B1015 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
87 | 06B1016 | BEAM DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
88 | 06C1000 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
89 | 06C1002 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
90 | 06C1006 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
91 | 06C1008 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
92 | 06C1009 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
93 | 06C1010 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
94 | 06C1011 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
95 | 06C1012 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
96 | 06C1013 | COLUMN DETAIL |  | 28-07-2025 |  | ISSUED FOR FABRICATION
97 | 06C1014 | COLUMN DETAIL |  | 28-07-2025 |  | ISSUED FOR FABRICATION
98 | 06C1015 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
99 | 06C1016 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION
100 | 06C1017 | COLUMN DETAIL | 11-06-2025 | 28-07-2025 |  | ISSUED FOR FABRICATION