## Drawing Log
OUTGOING DRAWING LOG SHEET
Project Name : frame |  |  |  | Client : infra
Sl. No | Sheet No | Drawing Title | Sent for Approval |  | Sent for Fabrication | Remarks
|  |  | Rev A | Rev BE | Rev 0
DRAWINGS
1 | 02B1001 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
2 | 02B1002 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
3 | 02B1003 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
4 | 02B1004 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
5 | 02B1005 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
6 | 02B1006 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
7 | 02B1007 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
8 | 02B1008 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
9 | 02B1009 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
10 | 02B1010 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
11 | 02B1011 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
12 | 02B1012 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
13 | 02B1013 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
14 | 02B1014 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
15 | 02B1015 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
16 | 02B1016 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
17 | 02B1017 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
18 | 02B1018 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
19 | 02B1019 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
20 | 02B1020 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
21 | 02B1021 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
22 | 02B1022 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
23 | 02B1023 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
24 | 02B1024 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
25 | 02B1025 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
26 | 02B1026 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
27 | 02B1027 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
28 | 02B1028 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
29 | 02B1029 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
30 | 02B1030 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
31 | 02B1031 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
32 | 02B1032 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
33 | 02B1033 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
34 | 02B1034 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
35 | 02B1035 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
36 | 02B1036 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
37 | 02B1037 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
38 | 02B1040 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
39 | 02B1041 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
40 | 02C1000 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
41 | 02C1001 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
42 | 02C1002 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
43 | 02C1003 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
44 | 02C1004 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
45 | 02C1005 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
46 | 02C1006 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
47 | 02C1007 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
48 | 02C1008 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
49 | 02C1009 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
50 | 02C1010 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
51 | 02C1011 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
52 | 02C1012 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
53 | 02C1013 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
54 | 02C1014 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
55 | 02C1015 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
56 | 02C1016 | COLUMN DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
57 | 02D1000 | HORIZONTAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
58 | 02D1001 | HORIZONTAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
59 | 02D1002 | HORIZONTAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
60 | 02D1003 | HORIZONTAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
61 | 02D1004 | VERTICAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
62 | 02D1005 | VERTICAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
63 | 02D1006 | VERTICAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
64 | 02D1007 | VERTICAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
65 | 02D1008 | VERTICAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
66 | 02D1009 | VERTICAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
67 | 02D1010 | VERTICAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
68 | 02D1011 | VERTICAL BRACE | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
69 | 02M1000 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
70 | 02M1001 | PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
71 | 02M1002 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
72 | 02M1003 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
73 | 02M1004 | PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
74 | 02M1005 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
75 | 02M1006 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
76 | 02M1007 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
77 | 02M1008 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
78 | 02M1009 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
79 | 02M1010 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
80 | 02M1011 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
81 | 02M1013 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
82 | 02M1014 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
83 | 02M1015 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
84 | 02M1016 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
85 | 02M1017 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
86 | 02M1018 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
87 | 02M1019 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
88 | 02M1020 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
89 | 02M1021 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
90 | 02M1022 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
91 | 02M1023 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
92 | 02M1024 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
93 | 02M1025 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
94 | 02M1026 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
95 | 02M1027 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
96 | 02M1028 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
97 | 02M1029 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
98 | 02M1030 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
99 | 02M1031 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
100 | 02M1032 | PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
101 | 02M1033 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
102 | 02M1034 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
103 | 02M1035 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
104 | 02M1036 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
105 | 02M1037 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
106 | 02M1038 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
107 | 02M1039 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
108 | 03B1000 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
109 | 03B1002 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
110 | 03B1003 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
111 | 03B1004 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
112 | 03B1005 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
113 | 03B1008 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
114 | 03B1010 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
115 | 03B1011 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
116 | 03B1012 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
117 | 03B1013 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
118 | 03B1014 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
119 | 03B1015 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
120 | 03B1016 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
121 | 03B1017 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
122 | 03B1018 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
123 | 03B1019 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
124 | 03B1020 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
125 | 03B1021 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
126 | 03B1022 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
127 | 03B1023 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
128 | 03B1024 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
129 | 03B1025 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
130 | 03B1026 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
131 | 03B1027 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
132 | 03B1028 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
133 | 03B1029 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
134 | 03B1030 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
135 | 03B1031 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
136 | 03B1032 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
137 | 03B1033 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
138 | 03B1034 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
139 | 03B1035 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
140 | 03B1036 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
141 | 03B1037 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
142 | 03B1042 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
143 | 03B1044 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
144 | 03B1045 | BEAM DETAIL | 11-06-2025 |  |  | ISSUED FOR APPROVAL
145 | 03B1046 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
146 | 03B1047 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
147 | 03B1048 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
148 | 03B1049 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
149 | 03B1050 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
150 | 03B1051 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
151 | 03B1052 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
152 | 03C1000 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
153 | 03C1001 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
154 | 03C1002 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
155 | 03C1003 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
156 | 03C1004 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025
157 | 03C1005 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
158 | 03C1008 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
159 | 03C1009 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
160 | 03C1010 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
161 | 03C1011 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
162 | 03C1012 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
163 | 03C1013 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
164 | 03C1014 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
165 | 03C1015 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
166 | 03C1016 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
167 | 03D1000 | HORIZONTAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
168 | 03D1001 | HORIZONTAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
169 | 03D1002 | HORIZONTAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
170 | 03D1003 | HORIZONTAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
171 | 03D1004 | HORIZONTAL BRACE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
172 | 03D1005 | HORIZONTAL BRACE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
173 | 03M1000 | BACKING BAR DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
174 | 03M1001 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
175 | 03M1004 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
176 | 03M1005 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
177 | 03M1008 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
178 | 03M1009 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
179 | 03M1010 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
180 | 03M1011 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
181 | 03M1012 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
182 | 03M1013 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
183 | 03M1014 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
184 | 03M1015 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
185 | 03M1016 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
186 | 03M1017 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
187 | 03M1018 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
188 | 03M1019 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
189 | 03M1020 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
190 | 03M1021 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
191 | 03M1022 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
192 | 03M1023 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
193 | 03M1024 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
194 | 03M1025 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
195 | 03M1026 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
196 | 03M1027 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
197 | 03M1028 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
198 | 03M1029 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
199 | 03M1030 | PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
200 | 03M1031 | FRAME DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
201 | 03M1032 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
202 | 04B1000 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
203 | 04B1001 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
204 | 04B1002 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
205 | 04B1003 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
206 | 04B1004 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
207 | 04B1005 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
208 | 04B1006 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
209 | 04B1007 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
210 | 04B1008 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
211 | 04B1009 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
212 | 04B1010 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
213 | 04B1011 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
214 | 04B1013 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
215 | 04B1014 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
216 | 04B1015 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
217 | 04B1016 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
218 | 04B1017 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
219 | 04B1018 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
220 | 04B1019 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
221 | 04B1021 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
222 | 04C1000 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
223 | 04C1001 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
224 | 04C1002 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
225 | 04C1007 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
226 | 04C1008 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
227 | 04C1009 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
228 | 04D1000 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
229 | 04D1001 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
230 | 04D1002 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
231 | 04D1003 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
232 | 04D1004 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
233 | 04D1005 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
234 | 04M1000 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
235 | 04M1001 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
236 | 04M1002 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
237 | 04M1003 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
238 | 04M1004 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
239 | 04M1005 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
240 | 04M1006 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
241 | 04M1007 | PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
242 | 04M1008 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
243 | 04M1009 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
244 | 04M1010 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
245 | 04M1012 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
246 | 04M1013 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
247 | 04M1014 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
248 | 04M1015 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
249 | 04M1016 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
250 | 04M1017 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
251 | 04M1018 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
252 | 04M1019 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
253 | 04M1020 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
254 | 04M1021 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
255 | 04M1022 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
256 | 04M1023 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
257 | 04M1025 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
258 | 04M1026 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
259 | 04M1027 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
260 | 04M1028 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
261 | 04M1029 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
262 | 04M1030 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
263 | 04M1031 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
264 | 04M1032 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
265 | 04M1033 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
266 | 04M1034 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
267 | 04M1035 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
268 | 04M1037 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
269 | 04M1038 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
270 | 04M1039 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
271 | 04M1040 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
272 | 04M1041 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
273 | 04M1042 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
274 | 04M1043 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
275 | 04M1044 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
276 | 04M1045 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
277 | 04M1046 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
278 | 04M1047 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
279 | 04M1048 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
280 | 04M1052 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
281 | 04M1053 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
282 | 04M1054 | FRAME DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
283 | 04M1055 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
284 | 04M1056 | PLATE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
285 | 04M1057 | PLATE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
286 | 04M1058 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
287 | 04M1059 | FRAME DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
288 | 04M1060 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
289 | 04M1061 | HSS DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
290 | 05B1000 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
291 | 05B1001 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
292 | 05B1002 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
293 | 05B1003 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
294 | 05B1004 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
295 | 05B1005 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
296 | 05B1006 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
297 | 05B1007 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
298 | 05B1008 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
299 | 05B1009 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
300 | 05B1016 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
301 | 05B1021 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
302 | 05C1001 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
303 | 05C1006 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
304 | 05C1010 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
305 | 05C1011 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
306 | 05C1012 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
307 | 05C1013 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
308 | 05C1014 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
309 | 05C1015 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
310 | 05C1016 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
311 | 05M1000 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
312 | 05M1001 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
313 | 05M1002 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
314 | 05M1003 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
315 | 05M1004 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
316 | 05M1005 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
317 | 05M1010 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
318 | 05M1011 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
319 | 05M1012 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
320 | 05M1013 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
321 | 05M1014 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
322 | 05M1015 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
323 | 05M1016 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
324 | 05M1017 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
325 | 05M1018 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
326 | 05M1019 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
327 | 05M1020 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
328 | 05M1021 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
329 | 05M1022 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
330 | 05M1023 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
331 | 05M1024 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
332 | 05M1025 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
333 | 06B1000 | BEAM DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
334 | 06B1001 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
335 | 06B1002 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
336 | 06B1003 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
337 | 06B1004 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
338 | 06B1005 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
339 | 06B1006 | BEAM DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
340 | 06B1007 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
341 | 06B1008 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
342 | 06B1009 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
343 | 06B1010 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
344 | 06B1011 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
345 | 06B1012 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
346 | 06B1013 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
347 | 06B1014 | BEAM DETAIL |  | 11-06-2025 |  | CENTERED TO MAIN MEMBER U.N.O. A GSV ISSUED FOR APPROVAL
348 | 06B1015 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
349 | 06B1016 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
350 | 06B1025 | BEAM DETAIL |  | 11-06-2025 | 28-07-2025 | ISSUED FOR FABRICATION
351 | 06B1028 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
352 | 06B1030 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
353 | 06B1033 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
354 | 06B1034 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
355 | 06B1035 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
356 | 06B1036 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
357 | 06B1037 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
358 | 06B1038 | BEAM DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
359 | 06C1000 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
360 | 06C1002 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
361 | 06C1006 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
362 | 06C1008 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
363 | 06C1009 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
364 | 06C1010 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
365 | 06C1011 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
366 | 06C1012 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
367 | 06C1013 | COLUMN DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
368 | 06C1014 | COLUMN DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
369 | 06C1015 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
370 | 06C1016 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
371 | 06C1017 | COLUMN DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
372 | 06D1000 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
373 | 06D1001 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
374 | 06D1002 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
375 | 06D1003 | VERTICAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
376 | 06D1004 | HARIZONTAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
377 | 06D1005 | HARIZONTAL BRACE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
378 | 06M1000 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
379 | 06M1001 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
380 | 06M1002 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
381 | 06M1003 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
382 | 06M1004 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
383 | 06M1005 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
384 | 06M1006 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
385 | 06M1007 | CHANNEL DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
386 | 06M1008 | ANGLE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
387 | 06M1013 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
388 | 06M1014 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
389 | 06M1015 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
390 | 06M1016 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
391 | 06M1017 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
392 | 06M1018 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
393 | 06M1019 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
394 | 06M1020 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
395 | 06M1021 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
396 | 06M1022 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
397 | 06M1023 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
398 | 06M1024 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
399 | 06M1025 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
400 | 06M1026 | BENT PLATE DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
401 | 06M1027 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
402 | 06M1028 | FRAME DETAIL | 11-06-2025 |  | 28-07-2025 | ISSUED FOR FABRICATION
403 | 06M1029 | FRAME DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
404 | 06M1030 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
405 | 06M1031 | HSS DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
406 | 06M1032 | ANGLE DETAIL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
407 | a12 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
408 | a14 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
409 | a39 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
410 | a40 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
411 | a46 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
412 | a53 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
413 | a54 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
414 | a74 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
415 | a75 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
416 | a78 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
417 | a81 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
418 | a83 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
419 | a86 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
420 | a87 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
421 | a88 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
422 | a89 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
423 | a90 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
424 | a91 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
425 | a92 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
426 | a93 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
427 | a97 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
428 | a99 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
429 | a100 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
430 | a101 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
431 | a102 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
432 | a103 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
433 | a106 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
434 | a107 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
435 | a108 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
436 | a109 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
437 | a110 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
438 | a111 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
439 | a112 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
440 | a113 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
441 | a118 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
442 | a119 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
443 | a120 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
444 | a124 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
445 | a134 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
446 | a135 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
447 | a169 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
448 | a170 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
449 | a177 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
450 | a178 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
451 | a179 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
452 | a188 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
453 | a215 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
454 | a250 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
455 | a263 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
456 | a267 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
457 | a269 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
458 | a271 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
459 | a272 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
460 | a273 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
461 | a274 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
462 | a276 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
463 | a279 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
464 | a280 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
465 | a282 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
466 | a286 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
467 | a287 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
468 | a292 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
469 | a293 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
470 | a294 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
471 | a295 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
472 | a296 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
473 | a298 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
474 | a299 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
475 | a300 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
476 | a301 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
477 | a305 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
478 | a306 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
479 | a307 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
480 | a311 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
481 | a313 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
482 | a328 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
483 | a341 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
484 | a343 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
485 | a345 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
486 | a346 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
487 | a347 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
488 | a348 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
489 | a350 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
490 | a351 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
491 | a353 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
492 | a354 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
493 | a355 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
494 | a356 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
495 | a357 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
496 | a358 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
497 | a360 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
498 | a362 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
499 | a827 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
500 | a829 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
501 | a831 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
502 | a832 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
503 | a839 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
504 | a840 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
505 | a854 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
506 | a873 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
507 | a875 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
508 | a876 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
509 | a880 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
510 | a882 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
511 | a893 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
512 | a897 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
513 | a898 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
514 | a903 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
515 | a905 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
516 | a906 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
517 | a914 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
518 | a915 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
519 | a916 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
520 | a923 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
521 | a939 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
522 | a941 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
523 | a959 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
524 | a960 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
525 | a965 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
526 | a975 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
527 | a980 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
528 | a981 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
529 | a982 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
530 | a984 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
531 | a985 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
532 | a986 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
533 | a994 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
534 | a1005 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
535 | a1020 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
536 | a1021 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
537 | a1031 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
538 | a1032 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
539 | a1040 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
540 | a1065 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
541 | a1067 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
542 | a1094 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
543 | a1095 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
544 | a1133 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
545 | a1155 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
546 | a1161 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
547 | a1163 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
548 | a1172 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
549 | a1346 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
550 | a1349 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
551 | a1350 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
552 | a1352 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
553 | a1354 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
554 | a1355 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
555 | a1356 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
556 | a1365 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
557 | a1368 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
558 | a1380 | ANGLE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
559 | bp7 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
560 | bp8 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
561 | bp9 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
562 | bp10 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
563 | bp11 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
564 | bp12 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
565 | bp13 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
566 | bp14 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
567 | bp15 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
568 | bp16 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
569 | bp17 | BASE PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
570 | bpl19 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
571 | bpl28 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
572 | bpl31 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
573 | bpl32 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
574 | bpl64 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
575 | bpl65 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
576 | bpl70 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
577 | bpl71 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
578 | bpl76 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
579 | bpl78 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
580 | bpl86 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
581 | bpl90 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
582 | bpl91 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
583 | bpl500 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
584 | bpl505 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
585 | bpl518 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
586 | bpl525 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
587 | bpl526 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
588 | bpl527 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
589 | bpl533 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
590 | bpl538 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
591 | bpl575 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
592 | bpl577 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
593 | bpl578 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
594 | bpl627 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
595 | bpl628 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
596 | bpl645 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
597 | bpl647 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
598 | bpl651 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
599 | bpl653 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
600 | bpl743 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
601 | bpl745 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
602 | bpl1903 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
603 | bpl1907 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
604 | bpl1920 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
605 | bpl1922 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
606 | bpl1923 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
607 | bpl1941 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
608 | bpl1942 | BENT PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
609 | ch35 | CHANNEL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
610 | ch81 | CHANNEL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
611 | ch82 | CHANNEL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
612 | ch83 | CHANNEL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
613 | ch348 | CHANNEL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
614 | ch350 | CHANNEL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
615 | ch354 | CHANNEL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
616 | ch359 | CHANNEL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
617 | ch362 | CHANNEL |  |  | 28-07-2025 | ISSUED FOR FABRICATION
618 | cp3 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
619 | cp4 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
620 | hss184 | HSS |  |  | 28-07-2025 | ISSUED FOR FABRICATION
621 | hss1191 | HSS |  |  | 28-07-2025 | ISSUED FOR FABRICATION
622 | hss1192 | HSS |  |  | 28-07-2025 | ISSUED FOR FABRICATION
623 | pl18 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
624 | pl61 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
625 | pl161 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
626 | pl188 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
627 | pl200 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
628 | pl213 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
629 | pl232 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
630 | pl247 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
631 | pl255 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
632 | pl258 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
633 | pl274 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
634 | pl275 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
635 | pl281 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
636 | pl290 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
637 | pl300 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
638 | pl301 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
639 | pl304 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
640 | pl306 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
641 | pl310 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
642 | pl315 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
643 | pl316 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
644 | pl317 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
645 | pl327 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
646 | pl332 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
647 | pl336 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
648 | pl337 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
649 | pl338 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
650 | pl339 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
651 | pl340 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
652 | pl341 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
653 | pl342 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
654 | pl345 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
655 | pl346 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
656 | pl348 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
657 | pl349 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
658 | pl352 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
659 | pl355 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
660 | pl357 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
661 | pl358 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
662 | pl359 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
663 | pl360 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
664 | pl361 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
665 | pl362 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
666 | pl365 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
667 | pl366 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
668 | pl367 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
669 | pl369 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
670 | pl370 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
671 | pl371 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
672 | pl372 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
673 | pl375 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
674 | pl376 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
675 | pl377 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
676 | pl379 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
677 | pl380 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
678 | pl381 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
679 | pl388 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
680 | pl390 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
681 | pl391 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
682 | pl393 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
683 | pl394 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
684 | pl395 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
685 | pl397 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
686 | pl404 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
687 | pl407 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
688 | pl409 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
689 | pl412 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
690 | pl414 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
691 | pl415 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
692 | pl425 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
693 | pl426 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
694 | pl428 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
695 | pl435 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
696 | pl439 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
697 | pl450 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
698 | pl907 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
699 | pl910 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
700 | pl912 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
701 | pl933 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
702 | pl934 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
703 | pl936 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
704 | pl937 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
705 | pl943 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
706 | pl944 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
707 | pl951 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
708 | pl962 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
709 | pl965 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
710 | pl970 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
711 | pl973 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
712 | pl976 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
713 | pl977 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
714 | pl978 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
715 | pl979 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
716 | pl980 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
717 | pl981 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
718 | pl982 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
719 | pl985 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
720 | pl988 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
721 | pl990 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
722 | pl991 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
723 | pl992 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
724 | pl995 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
725 | pl999 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
726 | pl1011 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
727 | pl1012 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
728 | pl1013 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
729 | pl1015 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
730 | pl1016 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
731 | pl1017 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
732 | pl1018 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
733 | pl1019 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
734 | pl1020 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
735 | pl1021 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
736 | pl1022 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
737 | pl1024 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
738 | pl1032 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
739 | pl1035 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
740 | pl1041 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
741 | pl1044 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
742 | pl1045 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
743 | pl1046 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
744 | pl1047 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
745 | pl1048 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
746 | pl1061 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
747 | pl1065 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
748 | pl1066 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
749 | pl1070 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
750 | pl1072 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
751 | pl1076 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
752 | pl1079 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
753 | pl1080 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
754 | pl1090 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
755 | pl1091 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
756 | pl1092 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
757 | pl1093 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
758 | pl1094 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
759 | pl1095 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
760 | pl1103 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
761 | pl1109 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
762 | pl1110 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
763 | pl1113 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
764 | pl1118 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
765 | pl1119 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
766 | pl1123 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
767 | pl1124 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
768 | pl1128 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
769 | pl1129 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
770 | pl1130 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
771 | pl1131 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
772 | pl1132 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
773 | pl1133 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
774 | pl1134 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
775 | pl1135 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
776 | pl1138 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
777 | pl1139 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
778 | pl1140 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
779 | pl1141 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
780 | pl1142 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
781 | pl1143 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
782 | pl1153 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
783 | pl1160 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
784 | pl1161 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
785 | pl1162 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
786 | pl1163 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
787 | pl1164 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
788 | pl1165 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
789 | pl1308 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
790 | pl1310 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
791 | pl1313 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
792 | pl1315 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
793 | pl1379 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
794 | pl1383 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
795 | pl1384 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
796 | pl1389 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
797 | pl1418 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
798 | pl1419 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
799 | pl1568 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
800 | pl1570 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
801 | pl1637 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION
802 | pl1673 | PLATE |  |  | 28-07-2025 | ISSUED FOR FABRICATION