## Drawing Log
OUTGOING DRAWING LOG SHEET
Project Name : tower |  |  |  |  | Client : daf
Sl. No | Sheet No | Drawing Title | Sent for Approval |  |  | Sent for Fabrication |  |  | Remarks
|  |  | Rev A | Rev B | Rev C | Rev 0 | Rev 1 | Rev 2
DRAWINGS
1 | a738 | ANGLE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
2 | a1095 | ANGLE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
3 | a1136 | ANGLE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
4 | a2573 | ANGLE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
5 | a3514 | ANGLE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
6 | bp1000 | BASE PLATE
7 | bp1001 | BASE PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
8 | bpl1994 | BENT PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
9 | cp1000 | CAP PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
10 | cp1001 | CAP PLATE |  |  |  | 09-22-2025 | 09-23-2025 | 09-25-2025 | REVISED AS NOTED
11 | E-03.00 | SOW #03 -SOUTH WEST FRAMING | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
12 | E-03.00A | SOW #03 -SOUTH WEST FRAMING |  |  |  | 09-25-2025 |  |  | FOR CONSTRUCTION
13 | E-03.01 | SOW #03 -SOUTH WEST FRAMING | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
14 | E-03.01A | SOW #03 -SOUTH WEST FRAMING | 06-23-2025 | 08-22-2025 |  | 09-25-2025 |  |  | FOR CONSTRUCTION
15 | E-03.01B | SOW #03 -SOUTH WEST FRAMING | 06-23-2025 | 08-22-2025 |  | 09-25-2025 |  |  | FOR CONSTRUCTION
16 | E-03.01C | SOW #03 -SOUTH WEST MISC | 06-23-2025 | 08-22-2025 |  | 09-25-2025 |  |  | FOR CONSTRUCTION
17 | E-03.01D | SOW #03 -SOUTH WEST MISC | 06-23-2025 | 08-22-2025 |  | 09-25-2025 |  |  | FOR CONSTRUCTION
18 | E-03.01E | SOW #03 -SOUTH WEST MISC |  |  |  | 08-22-2025 |  |  | FOR CONSTRUCTION 09-25-2025 1 A FOR APPROVAL
19 | E-03.01F | SOW #03 -SOUTH WEST MISC |  |  |  | 09-25-2025 |  |  | FOR CONSTRUCTION
20 | E-03.02 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
21 | E-03.03 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 02-27-2025 | 06-23-2025 |  | 08-22-2025 |  |  | FOR CONSTRUCTION 09-25-2025 3 C FOR RE-APPROVAL
22 | E-03.04 | SOW #03 -SOUTH WEST FRAMING ELEVATION VIEWS | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
23 | E-03.05 | SOW #03 -SOUTH WEST FRAMING | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
24 | E-03.06 | SOW #03 -SOUTH WEST FRAMING | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
25 | E-03.07 | SOW #03 -SOUTH WEST FRAMING SECTIONS Scale VARIES TUORG KNIRHS-NON | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
26 | E-03.08 | SOW #03 -SOUTH WEST FRAMING | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
27 | E-03.09 | SOW #03 -SOUTH WEST FRAMING | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
28 | E-03.10 | SOW #03 -SOUTH WEST FRAMING | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-25-2025 |  |  | FOR CONSTRUCTION
29 | F-03.00 | PLATE DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 |  |  | FOR FABRICATION
30 | F-03.01 | COLUMN DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 |  | 09-25-2025 | REVISED AS NOTED
31 | F-03.02 | COLUMN DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 | 09-25-2025 |  | REVISED AS NOTED
32 | F-03.03 | COLUMN DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 |  |  | FOR FABRICATION
33 | F-03.04 | COLUMN DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 |  |  | FOR FABRICATION
34 | F-03.05 | COLUMN & BEAM DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 | 09-25-2025 |  | REVISED AS NOTED
35 | F-03.06 | BEAM DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 | 09-25-2025 |  | REVISED AS NOTED
36 | F-03.07 | BEAM DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 |  |  | FOR FABRICATION
37 | F-03.08 | BEAM DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 |  |  | FOR FABRICATION
38 | F-03.09 | BEAM DETAIL | 02-27-2025 | 06-23-2025 | 08-22-2025 | 09-22-2025 |  |  | FOR FABRICATION
39 | F-03.11 | MISCELLANEOUS DETAIL |  | 08-22-2025 |  | 09-22-2025 | 09-25-2025 |  | REVISED AS NOTED
40 | F-03.12 | MISCELLANEOUS DETAIL | 06-23-2025 | 08-22-2025 |  |  |  | 09-25-2025 | REVISED AS NOTED
41 | pl462 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
42 | pl470 | PLATE |  |  |  | 09-22-2025 | 09-25-2025 |  | REVISED AS NOTED
43 | pl472 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
44 | pl473 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
45 | pl658 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
46 | pl665 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
47 | pl680 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
48 | pl1517 | PLATE
49 | pl1550 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
50 | pl1608 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
51 | pl2938 | PLATE |  |  |  | 09-22-2025 | 09-25-2025 |  | REVISED AS NOTED
52 | pl3056 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
53 | pl3057 | PLATE
54 | pl3732 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
55 | pl3738 | PLATE |  |  |  | 09-22-2025 | 09-25-2025 |  | REVISED AS NOTED
56 | pl3739 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
57 | pl3740 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
58 | pl3742 | PLATE |  |  |  | 09-22-2025 |  |  | FOR FABRICATION
59 | pl3749 | PLATE |  |  |  | 09-25-2025 |  |  | FOR FABRICATION