## Drawing Log
Sl. No. | Sheet No. | Drawing Title | Revision Mark | Date | Remarks | Original Filename
SHOP DRAWING
1 | a1005 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1005_0.pdf
2 | a103 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a103_0.pdf
3 | a1040 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1040_0.pdf
4 | a100 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a100_0.pdf
5 | a101 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a101_0.pdf
6 | a1020 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1020_0.pdf
7 | a108 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a108_0.pdf
8 | a1067 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1067_0.pdf
9 | a1065 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1065_0.pdf
10 | a1021 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1021_0.pdf
11 | a102 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a102_0.pdf
12 | a109 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a109_0.pdf
13 | a106 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a106_0.pdf
14 | a1094 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1094_0.pdf
15 | a1095 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1095_0.pdf
16 | a110 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a110_0.pdf
17 | a112 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a112_0.pdf
18 | a111 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a111_0.pdf
19 | a1161 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1161_0.pdf
20 | a1032 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1032_0.pdf
21 | a107 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a107_0.pdf
22 | a1133 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1133_0.pdf
23 | a113 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a113_0.pdf
24 | a1031 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1031_0.pdf
25 | a1155 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1155_0.pdf
26 | a118 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a118_0.pdf
27 | a1172 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1172_0.pdf
28 | a1163 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1163_0.pdf
29 | a119 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a119_0.pdf
30 | a120 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a120_0.pdf
31 | a124 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a124_0.pdf
32 | a1346 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1346_0.pdf
33 | a1350 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1350_0.pdf
34 | a134 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a134_0.pdf
35 | a1349 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1349_0.pdf
36 | a12 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a12_0.pdf
37 | a188 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a188_0.pdf
38 | a1356 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1356_0.pdf
39 | a1352 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1352_0.pdf
40 | a1355 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1355_0.pdf
41 | a1354 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1354_0.pdf
42 | a263 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a263_0.pdf
43 | a269 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a269_0.pdf
44 | a271 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a271_0.pdf
45 | a273 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a273_0.pdf
46 | a267 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a267_0.pdf
47 | a250 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a250_0.pdf
48 | a215 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a215_0.pdf
49 | a1380 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1380_0.pdf
50 | a1368 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1368_0.pdf
51 | a272 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a272_0.pdf
52 | a135 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a135_0.pdf
53 | a274 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a274_0.pdf
54 | a14 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a14_0.pdf
55 | a170 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a170_0.pdf
56 | a1365 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a1365_0.pdf
57 | a169 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a169_0.pdf
58 | a178 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a178_0.pdf
59 | a177 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a177_0.pdf
60 | a179 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a179_0.pdf
61 | a276 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a276_0.pdf
62 | a279 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a279_0.pdf
63 | a280 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a280_0.pdf
64 | a286 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a286_0.pdf
65 | a287 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a287_0.pdf
66 | a282 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a282_0.pdf
67 | a293 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a293_0.pdf
68 | a296 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a296_0.pdf
69 | a298 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a298_0.pdf
70 | a299 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a299_0.pdf
71 | a294 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a294_0.pdf
72 | a295 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a295_0.pdf
73 | a292 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a292_0.pdf
74 | a305 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a305_0.pdf
75 | a306 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a306_0.pdf
76 | a311 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a311_0.pdf
77 | a307 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a307_0.pdf
78 | a328 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a328_0.pdf
79 | a300 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a300_0.pdf
80 | a341 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a341_0.pdf
81 | a313 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a313_0.pdf
82 | a301 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a301_0.pdf
83 | a345 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a345_0.pdf
84 | a346 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a346_0.pdf
85 | a343 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a343_0.pdf
86 | a347 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a347_0.pdf
87 | a348 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a348_0.pdf
88 | a350 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a350_0.pdf
89 | a351 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a351_0.pdf
90 | a353 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a353_0.pdf
91 | a354 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a354_0.pdf
92 | a355 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a355_0.pdf
93 | a356 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a356_0.pdf
94 | a358 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a358_0.pdf
95 | a362 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a362_0.pdf
96 | a39 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a39_0.pdf
97 | a357 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a357_0.pdf
98 | a54 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a54_0.pdf
99 | a46 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a46_0.pdf
100 | a40 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a40_0.pdf
101 | a360 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a360_0.pdf
102 | a78 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a78_0.pdf
103 | a74 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a74_0.pdf
104 | a53 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a53_0.pdf
105 | a827 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a827_0.pdf
106 | a75 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a75_0.pdf
107 | a81 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a81_0.pdf
108 | a831 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a831_0.pdf
109 | a829 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a829_0.pdf
110 | a840 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a840_0.pdf
111 | a83 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a83_0.pdf
112 | a839 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a839_0.pdf
113 | a832 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a832_0.pdf
114 | a854 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a854_0.pdf
115 | a86 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a86_0.pdf
116 | a873 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a873_0.pdf
117 | a875 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a875_0.pdf
118 | a876 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a876_0.pdf
119 | a882 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a882_0.pdf
120 | a87 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a87_0.pdf
121 | a880 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a880_0.pdf
122 | a88 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a88_0.pdf
123 | a893 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a893_0.pdf
124 | a897 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a897_0.pdf
125 | a898 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a898_0.pdf
126 | a906 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a906_0.pdf
127 | a905 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a905_0.pdf
128 | a89 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a89_0.pdf
129 | a903 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a903_0.pdf
130 | a914 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a914_0.pdf
131 | a915 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a915_0.pdf
132 | a939 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a939_0.pdf
133 | a90 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a90_0.pdf
134 | a916 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a916_0.pdf
135 | a923 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a923_0.pdf
136 | a941 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a941_0.pdf
137 | a91 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a91_0.pdf
138 | a92 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a92_0.pdf
139 | a965 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a965_0.pdf
140 | a959 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a959_0.pdf
141 | a93 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a93_0.pdf
142 | a960 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a960_0.pdf
143 | a975 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a975_0.pdf
144 | a97 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a97_0.pdf
145 | a985 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a985_0.pdf
146 | a981 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a981_0.pdf
147 | a980 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a980_0.pdf
148 | a982 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a982_0.pdf
149 | a984 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a984_0.pdf
150 | a986 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a986_0.pdf
151 | bp10 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp10_0.pdf
152 | a994 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a994_0.pdf
153 | a99 | ANGLE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | a99_0.pdf
154 | bp11 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp11_0.pdf
155 | bp12 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp12_0.pdf
156 | bp14 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp14_0.pdf
157 | bp15 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp15_0.pdf
158 | bp8 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp8_0.pdf
159 | bp13 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp13_0.pdf
160 | bp9 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp9_0.pdf
161 | bp7 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp7_0.pdf
162 | bp16 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp16_0.pdf
163 | bp17 | BASE PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bp17_0.pdf
164 | bpl1922 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl1922_0.pdf
165 | bpl1903 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl1903_0.pdf
166 | bpl1907 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl1907_0.pdf
167 | bpl1923 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl1923_0.pdf
168 | bpl1941 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl1941_0.pdf
169 | bpl1920 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl1920_0.pdf
170 | bpl1942 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl1942_0.pdf
171 | bpl31 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl31_0.pdf
172 | bpl28 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl28_0.pdf
173 | bpl19 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl19_0.pdf
174 | bpl32 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl32_0.pdf
175 | bpl500 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl500_0.pdf
176 | bpl505 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl505_0.pdf
177 | bpl525 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl525_0.pdf
178 | bpl518 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl518_0.pdf
179 | bpl526 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl526_0.pdf
180 | bpl527 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl527_0.pdf
181 | bpl533 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl533_0.pdf
182 | bpl575 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl575_0.pdf
183 | bpl538 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl538_0.pdf
184 | bpl577 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl577_0.pdf
185 | bpl578 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl578_0.pdf
186 | bpl627 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl627_0.pdf
187 | bpl628 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl628_0.pdf
188 | bpl645 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl645_0.pdf
189 | bpl647 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl647_0.pdf
190 | bpl64 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl64_0.pdf
191 | bpl65 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl65_0.pdf
192 | bpl70 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl70_0.pdf
193 | bpl651 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl651_0.pdf
194 | bpl71 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl71_0.pdf
195 | bpl76 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl76_0.pdf
196 | bpl745 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl745_0.pdf
197 | bpl653 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl653_0.pdf
198 | bpl78 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl78_0.pdf
199 | bpl743 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl743_0.pdf
200 | bpl86 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl86_0.pdf
201 | bpl90 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl90_0.pdf
202 | ch348 | CHANNEL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | ch348_0.pdf
203 | bpl91 | BENT PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | bpl91_0.pdf
204 | ch350 | CHANNEL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | ch350_0.pdf
205 | ch354 | CHANNEL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | ch354_0.pdf
206 | ch359 | CHANNEL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | ch359_0.pdf
207 | ch35 | CHANNEL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | ch35_0.pdf
208 | ch81 | CHANNEL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | ch81_0.pdf
209 | ch82 | CHANNEL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | ch82_0.pdf
210 | ch362 | CHANNEL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | ch362_0.pdf
211 | ch83 | CHANNEL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | ch83_0.pdf
212 | cp3 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | cp3_0.pdf
213 | cp4 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | cp4_0.pdf
214 | hss1191 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | hss1191_0.pdf
215 | hss1192 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | hss1192_0.pdf
216 | hss184 | HSS | 0 | 28-07-2025 | ISSUED FOR FABRICATION | hss184_0.pdf
217 | pl1011 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1011_0.pdf
218 | pl1012 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1012_0.pdf
219 | pl1018 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1018_0.pdf
220 | pl1016 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1016_0.pdf
221 | pl1015 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1015_0.pdf
222 | pl1019 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1019_0.pdf
223 | pl1013 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1013_0.pdf
224 | pl1017 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1017_0.pdf
225 | pl1021 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1021_0.pdf
226 | pl1020 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1020_0.pdf
227 | pl1022 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1022_0.pdf
228 | pl1024 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1024_0.pdf
229 | pl1035 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1035_0.pdf
230 | pl1032 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1032_0.pdf
231 | pl1044 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1044_0.pdf
232 | pl1041 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1041_0.pdf
233 | pl1045 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1045_0.pdf
234 | pl1048 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1048_0.pdf
235 | pl1047 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1047_0.pdf
236 | pl1046 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1046_0.pdf
237 | pl1061 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1061_0.pdf
238 | pl1065 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1065_0.pdf
239 | pl1066 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1066_0.pdf
240 | pl1070 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1070_0.pdf
241 | pl1072 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1072_0.pdf
242 | pl1076 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1076_0.pdf
243 | pl1079 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1079_0.pdf
244 | pl1080 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1080_0.pdf
245 | pl1090 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1090_0.pdf
246 | pl1091 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1091_0.pdf
247 | pl1093 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1093_0.pdf
248 | pl1094 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1094_0.pdf
249 | pl1095 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1095_0.pdf
250 | pl1092 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1092_0.pdf
251 | pl1110 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1110_0.pdf
252 | pl1109 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1109_0.pdf
253 | pl1103 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1103_0.pdf
254 | pl1119 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1119_0.pdf
255 | pl1113 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1113_0.pdf
256 | pl1118 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1118_0.pdf
257 | pl1123 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1123_0.pdf
258 | pl1131 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1131_0.pdf
259 | pl1124 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1124_0.pdf
260 | pl1130 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1130_0.pdf
261 | pl1132 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1132_0.pdf
262 | pl1129 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1129_0.pdf
263 | pl1134 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1134_0.pdf
264 | pl1128 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1128_0.pdf
265 | pl1135 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1135_0.pdf
266 | pl1133 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1133_0.pdf
267 | pl1138 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1138_0.pdf
268 | pl1139 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1139_0.pdf
269 | pl1140 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1140_0.pdf
270 | pl1142 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1142_0.pdf
271 | pl1141 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1141_0.pdf
272 | pl1143 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1143_0.pdf
273 | pl1163 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1163_0.pdf
274 | pl1164 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1164_0.pdf
275 | pl1162 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1162_0.pdf
276 | pl1161 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1161_0.pdf
277 | pl1160 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1160_0.pdf
278 | pl1165 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1165_0.pdf
279 | pl1153 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1153_0.pdf
280 | pl161 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl161_0.pdf
281 | pl1637 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1637_0.pdf
282 | pl1308 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1308_0.pdf
283 | pl1673 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1673_0.pdf
284 | pl1570 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1570_0.pdf
285 | pl1313 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1313_0.pdf
286 | pl18 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl18_0.pdf
287 | pl188 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl188_0.pdf
288 | pl1315 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1315_0.pdf
289 | pl200 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl200_0.pdf
290 | pl232 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl232_0.pdf
291 | pl247 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl247_0.pdf
292 | pl1379 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1379_0.pdf
293 | pl1310 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1310_0.pdf
294 | pl213 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl213_0.pdf
295 | pl1383 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1383_0.pdf
296 | pl1384 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1384_0.pdf
297 | pl1389 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1389_0.pdf
298 | pl1418 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1418_0.pdf
299 | pl1568 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1568_0.pdf
300 | pl1419 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl1419_0.pdf
301 | pl274 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl274_0.pdf
302 | pl258 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl258_0.pdf
303 | pl255 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl255_0.pdf
304 | pl300 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl300_0.pdf
305 | pl290 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl290_0.pdf
306 | pl281 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl281_0.pdf
307 | pl275 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl275_0.pdf
308 | pl301 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl301_0.pdf
309 | pl315 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl315_0.pdf
310 | pl304 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl304_0.pdf
311 | pl306 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl306_0.pdf
312 | pl310 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl310_0.pdf
313 | pl316 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl316_0.pdf
314 | pl332 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl332_0.pdf
315 | pl317 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl317_0.pdf
316 | pl339 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl339_0.pdf
317 | pl327 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl327_0.pdf
318 | pl338 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl338_0.pdf
319 | pl336 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl336_0.pdf
320 | pl337 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl337_0.pdf
321 | pl341 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl341_0.pdf
322 | pl342 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl342_0.pdf
323 | pl348 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl348_0.pdf
324 | pl345 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl345_0.pdf
325 | pl340 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl340_0.pdf
326 | pl349 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl349_0.pdf
327 | pl346 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl346_0.pdf
328 | pl352 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl352_0.pdf
329 | pl355 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl355_0.pdf
330 | pl357 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl357_0.pdf
331 | pl358 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl358_0.pdf
332 | pl359 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl359_0.pdf
333 | pl362 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl362_0.pdf
334 | pl360 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl360_0.pdf
335 | pl366 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl366_0.pdf
336 | pl365 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl365_0.pdf
337 | pl361 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl361_0.pdf
338 | pl369 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl369_0.pdf
339 | pl367 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl367_0.pdf
340 | pl395 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl395_0.pdf
341 | pl370 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl370_0.pdf
342 | pl397 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl397_0.pdf
343 | pl394 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl394_0.pdf
344 | pl391 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl391_0.pdf
345 | pl372 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl372_0.pdf
346 | pl404 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl404_0.pdf
347 | pl412 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl412_0.pdf
348 | pl407 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl407_0.pdf
349 | pl414 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl414_0.pdf
350 | pl409 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl409_0.pdf
351 | pl393 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl393_0.pdf
352 | pl371 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl371_0.pdf
353 | pl375 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl375_0.pdf
354 | pl376 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl376_0.pdf
355 | pl379 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl379_0.pdf
356 | pl380 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl380_0.pdf
357 | pl377 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl377_0.pdf
358 | pl381 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl381_0.pdf
359 | pl388 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl388_0.pdf
360 | pl425 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl425_0.pdf
361 | pl390 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl390_0.pdf
362 | pl415 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl415_0.pdf
363 | pl426 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl426_0.pdf
364 | pl428 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl428_0.pdf
365 | pl435 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl435_0.pdf
366 | pl439 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl439_0.pdf
367 | pl912 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl912_0.pdf
368 | pl910 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl910_0.pdf
369 | pl450 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl450_0.pdf
370 | pl907 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl907_0.pdf
371 | pl61 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl61_0.pdf
372 | pl936 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl936_0.pdf
373 | pl965 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl965_0.pdf
374 | pl933 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl933_0.pdf
375 | pl943 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl943_0.pdf
376 | pl934 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl934_0.pdf
377 | pl973 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl973_0.pdf
378 | pl937 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl937_0.pdf
379 | pl951 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl951_0.pdf
380 | pl944 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl944_0.pdf
381 | pl962 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl962_0.pdf
382 | pl970 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl970_0.pdf
383 | pl976 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl976_0.pdf
384 | pl977 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl977_0.pdf
385 | pl979 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl979_0.pdf
386 | pl978 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl978_0.pdf
387 | pl982 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl982_0.pdf
388 | pl980 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl980_0.pdf
389 | pl981 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl981_0.pdf
390 | pl985 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl985_0.pdf
391 | pl988 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl988_0.pdf
392 | pl990 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl990_0.pdf
393 | pl991 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl991_0.pdf
394 | pl995 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl995_0.pdf
395 | pl992 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl992_0.pdf
396 | pl999 | PLATE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | pl999_0.pdf
397 | 02B1034 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1034_0.pdf
398 | 02C1007 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1007_0.pdf
399 | 02B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1005_0.pdf
400 | 02C1009 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1009_0.pdf
401 | 02C1006 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1006_0.pdf
402 | 02B1009 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1009_0.pdf
403 | 02B1035 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1035_0.pdf
404 | 02B1006 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1006_0.pdf
405 | 02B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1008_0.pdf
406 | 02C1014 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1014_0.pdf
407 | 02B1018 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1018_0.pdf
408 | 02C1005 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1005_0.pdf
409 | 02C1004 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1004_0.pdf
410 | 02B1010 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1010_0.pdf
411 | 02B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1004_0.pdf
412 | 03B1000 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1000_0.pdf
413 | 02C1013 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1013_0.pdf
414 | 02C1012 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1012_0.pdf
415 | 02C1002 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1002_0.pdf
416 | 02C1011 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1011_0.pdf
417 | 03B1024 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1024_0.pdf
418 | 02B1007 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1007_0.pdf
419 | 02C1016 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1016_0.pdf
420 | 03C1004 | COLUMN DETAIL | 0 | 28-07-2025 |  | 03C1004_0.pdf
421 | 02C1003 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1003_0.pdf
422 | 02C1001 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1001_0.pdf
423 | 03B1010 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1010_0.pdf
424 | 03C1003 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1003_0.pdf
425 | 02B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1002_0.pdf
426 | 02B1001 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1001_0.pdf
427 | 03C1000 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1000_0.pdf
428 | 03C1001 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1001_0.pdf
429 | 03C1014 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1014_0.pdf
430 | 03C1013 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1013_0.pdf
431 | 04B1010 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1010_0.pdf
432 | 02C1000 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1000_0.pdf
433 | 03C1015 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1015_0.pdf
434 | 04B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1008_0.pdf
435 | 02B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1003_0.pdf
436 | 04B1011 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1011_0.pdf
437 | 04B1009 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1009_0.pdf
438 | 03C1016 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1016_0.pdf
439 | 04B1007 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1007_0.pdf
440 | 03C1009 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1009_0.pdf
441 | 03C1010 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1010_0.pdf
442 | 03C1011 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1011_0.pdf
443 | 02C1010 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1010_0.pdf
444 | 04C1001 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1001_0.pdf
445 | 03C1012 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1012_0.pdf
446 | 04C1009 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1009_0.pdf
447 | 04B1019 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1019_0.pdf
448 | 02C1015 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1015_0.pdf
449 | 04B1017 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1017_0.pdf
450 | 05B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1005_0.pdf
451 | 04B1018 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1018_0.pdf
452 | 04B1006 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1006_0.pdf
453 | 03C1002 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1002_0.pdf
454 | 04C1000 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1000_0.pdf
455 | 04C1008 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1008_0.pdf
456 | 05B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1008_0.pdf
457 | 05B1009 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1009_0.pdf
458 | 03C1005 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1005_0.pdf
459 | 05B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1016_0.pdf
460 | 05B1006 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1006_0.pdf
461 | 05B1021 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1021_0.pdf
462 | 05C1010 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1010_0.pdf
463 | 04C1002 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1002_0.pdf
464 | 05C1013 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1013_0.pdf
465 | 06B1000 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1000_0.pdf
466 | 05B1007 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1007_0.pdf
467 | 06B1007 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1007_0.pdf
468 | 06B1006 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1006_0.pdf
469 | 02B1015 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1015_0.pdf
470 | 02B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1016_0.pdf
471 | 05C1012 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1012_0.pdf
472 | 04B1021 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1021_0.pdf
473 | 05C1016 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1016_0.pdf
474 | 02B1019 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1019_0.pdf
475 | 02B1020 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1020_0.pdf
476 | 05C1006 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1006_0.pdf
477 | 05C1014 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1014_0.pdf
478 | 04B1013 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1013_0.pdf
479 | 04B1014 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1014_0.pdf
480 | 02B1022 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1022_0.pdf
481 | 02B1025 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1025_0.pdf
482 | 06B1015 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1015_0.pdf
483 | 02B1024 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1024_0.pdf
484 | 02B1017 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1017_0.pdf
485 | 05C1015 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1015_0.pdf
486 | 05B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1004_0.pdf
487 | 02B1014 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1014_0.pdf
488 | 03C1008 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03C1008_0.pdf
489 | 06B1001 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1001_0.pdf
490 | 02B1023 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1023_0.pdf
491 | 02B1012 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1012_0.pdf
492 | 06C1011 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1011_0.pdf
493 | 02B1030 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1030_0.pdf
494 | 02B1029 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1029_0.pdf
495 | 06C1008 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1008_0.pdf
496 | 02B1028 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1028_0.pdf
497 | 02B1027 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1027_0.pdf
498 | 02B1011 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1011_0.pdf
499 | 02B1026 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1026_0.pdf
500 | 02B1021 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1021_0.pdf
501 | 02B1013 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1013_0.pdf
502 | 06C1009 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1009_0.pdf
503 | 06B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1016_0.pdf
504 | 02B1036 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1036_0.pdf
505 | 02B1031 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1031_0.pdf
506 | 02B1033 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1033_0.pdf
507 | 02B1037 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1037_0.pdf
508 | 02M1000 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1000_0.pdf
509 | 02B1032 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1032_0.pdf
510 | 02D1008 | VERTICAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1008_0.pdf
511 | 02M1001 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1001_0.pdf
512 | 06C1015 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1015_0.pdf
513 | 02D1010 | VERTICAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1010_0.pdf
514 | 02D1011 | VERTICAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1011_0.pdf
515 | 02M1002 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1002_0.pdf
516 | 02D1007 | VERTICAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1007_0.pdf
517 | 02M1003 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1003_0.pdf
518 | 02M1004 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1004_0.pdf
519 | 02D1002 | HORIZONTAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1002_0.pdf
520 | 02B1041 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1041_0.pdf
521 | 02B1040 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02B1040_0.pdf
522 | 02D1003 | HORIZONTAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1003_0.pdf
523 | 02D1001 | HORIZONTAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1001_0.pdf
524 | 06C1012 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1012_0.pdf
525 | 02D1000 | HORIZONTAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1000_0.pdf
526 | 02D1004 | VERTICAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1004_0.pdf
527 | 05C1001 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1001_0.pdf
528 | 02D1009 | VERTICAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1009_0.pdf
529 | 02C1008 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1008_0.pdf
530 | 02M1005 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1005_0.pdf
531 | 02M1007 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1007_0.pdf
532 | 02D1005 | VERTICAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1005_0.pdf
533 | 02M1006 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1006_0.pdf
534 | 06C1010 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1010_0.pdf
535 | 02M1011 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1011_0.pdf
536 | 06C1000 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1000_0.pdf
537 | 02M1010 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1010_0.pdf
538 | 06C1002 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1002_0.pdf
539 | 02D1006 | VERTICAL BRACE | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02D1006_0.pdf
540 | 06C1017 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1017_0.pdf
541 | 02M1013 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1013_0.pdf
542 | 02M1014 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1014_0.pdf
543 | 02M1009 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1009_0.pdf
544 | 02M1008 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1008_0.pdf
545 | 06C1013 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1013_0.pdf
546 | 02M1016 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1016_0.pdf
547 | 02M1017 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1017_0.pdf
548 | 02M1018 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1018_0.pdf
549 | 02M1019 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1019_0.pdf
550 | 02M1023 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1023_0.pdf
551 | 02M1021 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1021_0.pdf
552 | 06C1016 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1016_0.pdf
553 | 02M1015 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1015_0.pdf
554 | 02M1020 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1020_0.pdf
555 | 02M1022 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1022_0.pdf
556 | 02M1027 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1027_0.pdf
557 | 02M1026 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1026_0.pdf
558 | 02M1033 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1033_0.pdf
559 | 02M1034 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1034_0.pdf
560 | 02M1029 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1029_0.pdf
561 | 02M1028 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1028_0.pdf
562 | 02M1030 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1030_0.pdf
563 | 02M1032 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1032_0.pdf
564 | 02M1031 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1031_0.pdf
565 | 02M1035 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1035_0.pdf
566 | 06C1006 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1006_0.pdf
567 | 02M1036 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1036_0.pdf
568 | 04C1007 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04C1007_0.pdf
569 | 02M1025 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1025_0.pdf
570 | 02M1037 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1037_0.pdf
571 | 02M1024 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1024_0.pdf
572 | 02M1039 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1039_0.pdf
573 | 02M1038 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02M1038_0.pdf
574 | 03B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1002_0.pdf
575 | 03B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1003_0.pdf
576 | 03B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1005_0.pdf
577 | 06C1014 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06C1014_0.pdf
578 | 03B1013 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1013_0.pdf
579 | 03B1015 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1015_0.pdf
580 | 03B1012 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1012_0.pdf
581 | 03B1019 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1019_0.pdf
582 | 03B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1008_0.pdf
583 | 03B1011 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1011_0.pdf
584 | 03B1028 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1028_0.pdf
585 | 03B1021 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1021_0.pdf
586 | 03B1030 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1030_0.pdf
587 | 03B1029 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1029_0.pdf
588 | 03B1023 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1023_0.pdf
589 | 03B1026 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1026_0.pdf
590 | 03B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1004_0.pdf
591 | 03B1025 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1025_0.pdf
592 | 03B1027 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1027_0.pdf
593 | 03B1014 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1014_0.pdf
594 | 03B1022 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1022_0.pdf
595 | 03B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1016_0.pdf
596 | 03B1018 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1018_0.pdf
597 | 03B1020 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1020_0.pdf
598 | 03B1031 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1031_0.pdf
599 | 03B1017 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1017_0.pdf
600 | 03B1032 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1032_0.pdf
601 | 03B1035 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1035_0.pdf
602 | 03B1036 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1036_0.pdf
603 | 03B1034 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1034_0.pdf
604 | 03B1033 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1033_0.pdf
605 | 03B1037 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1037_0.pdf
606 | 03B1049 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1049_0.pdf
607 | 03B1048 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1048_0.pdf
608 | 03M1001 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1001_0.pdf
609 | 03D1003 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1003_0.pdf
610 | 03D1004 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1004_0.pdf
611 | 03M1000 | BACKING BAR DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1000_0.pdf
612 | 03M1004 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1004_0.pdf
613 | 03D1005 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1005_0.pdf
614 | 03D1000 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1000_0.pdf
615 | 03D1001 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1001_0.pdf
616 | 03B1042 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1042_0.pdf
617 | 03D1002 | HORIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03D1002_0.pdf
618 | 03B1046 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1046_0.pdf
619 | 03B1051 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1051_0.pdf
620 | 03B1050 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1050_0.pdf
621 | 03B1047 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1047_0.pdf
622 | 03B1044 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1044_0.pdf
623 | 03B1045 | BEAM DETAIL | A | 11-06-2025 | ISSUED FOR APPROVAL | 03B1045_0.pdf
624 | 03B1052 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03B1052_0.pdf
625 | 03M1005 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1005_0.pdf
626 | 03M1008 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1008_0.pdf
627 | 03M1010 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1010_0.pdf
628 | 03M1009 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1009_0.pdf
629 | 03M1014 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1014_0.pdf
630 | 03M1011 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1011_0.pdf
631 | 03M1015 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1015_0.pdf
632 | 03M1025 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1025_0.pdf
633 | 03M1012 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1012_0.pdf
634 | 03M1016 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1016_0.pdf
635 | 03M1026 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1026_0.pdf
636 | 03M1021 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1021_0.pdf
637 | 03M1017 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1017_0.pdf
638 | 03M1020 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1020_0.pdf
639 | 03M1018 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1018_0.pdf
640 | 03M1019 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1019_0.pdf
641 | 03M1022 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1022_0.pdf
642 | 03M1027 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1027_0.pdf
643 | 03M1013 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1013_0.pdf
644 | 03M1023 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1023_0.pdf
645 | 03M1024 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1024_0.pdf
646 | 03M1028 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1028_0.pdf
647 | 03M1030 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1030_0.pdf
648 | 03M1029 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1029_0.pdf
649 | 03M1032 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1032_0.pdf
650 | 04B1000 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1000_0.pdf
651 | 03M1031 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 03M1031_0.pdf
652 | 04B1001 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1001_0.pdf
653 | 04B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1002_0.pdf
654 | 04B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1004_0.pdf
655 | 04M1004 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1004_0.pdf
656 | 04B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1003_0.pdf
657 | 04D1000 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1000_0.pdf
658 | 04D1003 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1003_0.pdf
659 | 04M1002 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1002_0.pdf
660 | 04M1010 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1010_0.pdf
661 | 04M1013 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1013_0.pdf
662 | 04D1004 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1004_0.pdf
663 | 04B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1005_0.pdf
664 | 04D1002 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1002_0.pdf
665 | 04M1005 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1005_0.pdf
666 | 04M1000 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1000_0.pdf
667 | 04D1005 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1005_0.pdf
668 | 04D1001 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04D1001_0.pdf
669 | 04M1006 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1006_0.pdf
670 | 04M1008 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1008_0.pdf
671 | 04M1003 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1003_0.pdf
672 | 04M1007 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1007_0.pdf
673 | 04M1009 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1009_0.pdf
674 | 04M1012 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1012_0.pdf
675 | 04M1001 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1001_0.pdf
676 | 04M1014 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1014_0.pdf
677 | 04B1015 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1015_0.pdf
678 | 04B1016 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04B1016_0.pdf
679 | 04M1015 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1015_0.pdf
680 | 04M1016 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1016_0.pdf
681 | 04M1017 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1017_0.pdf
682 | 04M1018 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1018_0.pdf
683 | 04M1021 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1021_0.pdf
684 | 04M1030 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1030_0.pdf
685 | 04M1025 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1025_0.pdf
686 | 04M1028 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1028_0.pdf
687 | 04M1020 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1020_0.pdf
688 | 04M1029 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1029_0.pdf
689 | 04M1032 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1032_0.pdf
690 | 04M1027 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1027_0.pdf
691 | 04M1040 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1040_0.pdf
692 | 04M1019 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1019_0.pdf
693 | 04M1034 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1034_0.pdf
694 | 04M1023 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1023_0.pdf
695 | 04M1037 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1037_0.pdf
696 | 04M1026 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1026_0.pdf
697 | 04M1043 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1043_0.pdf
698 | 04M1031 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1031_0.pdf
699 | 04M1041 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1041_0.pdf
700 | 04M1022 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1022_0.pdf
701 | 04M1035 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1035_0.pdf
702 | 04M1044 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1044_0.pdf
703 | 04M1033 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1033_0.pdf
704 | 04M1042 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1042_0.pdf
705 | 04M1039 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1039_0.pdf
706 | 04M1038 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1038_0.pdf
707 | 04M1045 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1045_0.pdf
708 | 04M1047 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1047_0.pdf
709 | 04M1046 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1046_0.pdf
710 | 04M1048 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1048_0.pdf
711 | 04M1060 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1060_0.pdf
712 | 04M1057 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1057_0.pdf
713 | 04M1058 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1058_0.pdf
714 | 04M1052 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1052_0.pdf
715 | 04M1055 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1055_0.pdf
716 | 04M1053 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1053_0.pdf
717 | 04M1061 | HSS DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1061_0.pdf
718 | 04M1059 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1059_0.pdf
719 | 05B1001 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1001_0.pdf
720 | 04M1054 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1054_0.pdf
721 | 04M1056 | PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 04M1056_0.pdf
722 | 05M1005 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1005_0.pdf
723 | 05M1003 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1003_0.pdf
724 | 05M1001 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1001_0.pdf
725 | 05M1010 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1010_0.pdf
726 | 05M1004 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1004_0.pdf
727 | 05M1012 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1012_0.pdf
728 | 05M1011 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1011_0.pdf
729 | 05M1000 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1000_0.pdf
730 | 05M1002 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1002_0.pdf
731 | 05B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1002_0.pdf
732 | 05M1013 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1013_0.pdf
733 | 05B1000 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1000_0.pdf
734 | 05B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05B1003_0.pdf
735 | 05M1015 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1015_0.pdf
736 | 05C1011 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05C1011_0.pdf
737 | 05M1014 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1014_0.pdf
738 | 05M1016 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1016_0.pdf
739 | 05M1018 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1018_0.pdf
740 | 05M1017 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1017_0.pdf
741 | 05M1019 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1019_0.pdf
742 | 05M1020 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1020_0.pdf
743 | 05M1025 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1025_0.pdf
744 | 05M1023 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1023_0.pdf
745 | 05M1021 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1021_0.pdf
746 | 06B1002 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1002_0.pdf
747 | 05M1022 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1022_0.pdf
748 | 06B1003 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1003_0.pdf
749 | 05M1024 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 05M1024_0.pdf
750 | 06B1010 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1010_0.pdf
751 | 06B1011 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1011_0.pdf
752 | 06B1013 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1013_0.pdf
753 | 06B1014 | BEAM DETAIL | BE | 11-06-2025 | CENTERED TO MAIN MEMBER U.N.O. A GSV ISSUED FOR APPROVAL | 06B1014_0.pdf
754 | 06B1009 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1009_0.pdf
755 | 06B1012 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1012_0.pdf
756 | 06B1008 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1008_0.pdf
757 | 06B1004 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1004_0.pdf
758 | 06B1033 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1033_0.pdf
759 | 06B1028 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1028_0.pdf
760 | 06B1036 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1036_0.pdf
761 | 06D1000 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1000_0.pdf
762 | 06B1025 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1025_0.pdf
763 | 06B1005 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1005_0.pdf
764 | 06B1035 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1035_0.pdf
765 | 06B1030 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1030_0.pdf
766 | 06D1004 | HARIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1004_0.pdf
767 | 06D1005 | HARIZONTAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1005_0.pdf
768 | 06B1034 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1034_0.pdf
769 | 06B1037 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1037_0.pdf
770 | 06D1002 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1002_0.pdf
771 | 06M1001 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1001_0.pdf
772 | 06D1001 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1001_0.pdf
773 | 06B1038 | BEAM DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06B1038_0.pdf
774 | 06M1003 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1003_0.pdf
775 | 06M1004 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1004_0.pdf
776 | 06M1002 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1002_0.pdf
777 | 06D1003 | VERTICAL BRACE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06D1003_0.pdf
778 | 06M1000 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1000_0.pdf
779 | 06M1005 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1005_0.pdf
780 | 06M1008 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1008_0.pdf
781 | 06M1006 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1006_0.pdf
782 | 06M1014 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1014_0.pdf
783 | 06M1013 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1013_0.pdf
784 | 06M1007 | CHANNEL DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1007_0.pdf
785 | 06M1016 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1016_0.pdf
786 | 06M1015 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1015_0.pdf
787 | 06M1017 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1017_0.pdf
788 | 06M1018 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1018_0.pdf
789 | 06M1020 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1020_0.pdf
790 | 06M1019 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1019_0.pdf
791 | 06M1021 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1021_0.pdf
792 | 06M1024 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1024_0.pdf
793 | 06M1022 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1022_0.pdf
794 | 06M1023 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1023_0.pdf
795 | 06M1030 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1030_0.pdf
796 | 06M1025 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1025_0.pdf
797 | 06M1032 | ANGLE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1032_0.pdf
798 | 06M1031 | HSS DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1031_0.pdf
799 | 06M1026 | BENT PLATE DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1026_0.pdf
800 | 06M1027 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1027_0.pdf
801 | 06M1028 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1028_0.pdf
802 | 06M1029 | FRAME DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 06M1029_0.pdf
803 | 02C1001 | COLUMN DETAIL | 0 | 28-07-2025 | ISSUED FOR FABRICATION | 02C1001_0.pdf